## Sprint Report
Team | Sprint | Story Points Committed | Story Ponts Committed VC | Story Points Added | Story Points Removed | Story Points Not Completed | Story Points Completed | Story Points Completed VC | % Complete | # Issues Committed | # Issues Added | # Issues Removed | # Issues Not Completed | # Issues Completed | % Complete
JAMP Team 2 | API-JAMP Sprint 1.1 |  |  | 0 |  | 34 |  |  |  | 8 | 0 | 0 | 8 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 1.2 |  |  | 0 |  | 25 |  |  |  | 7 | 0 | 0 | 7 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 1.3 |  |  | 0 |  | 11 |  |  |  | 6 | 0 | 0 | 6 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 1.4 |  |  | 0 |  | 35 |  |  |  | 10 | 0 | 0 | 10 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 1.5 |  |  | 0 |  | 25 |  |  |  | 6 | 0 | 0 | 6 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 2.1 |  |  | 0 |  | 27 |  |  |  | 10 | 0 | 0 | 10 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 2.2 |  |  | 0 |  | 27 |  |  |  | 7 | 0 | 0 | 7 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 2.3 |  |  | 0 |  | 15 |  |  |  | 5 | 0 | 0 | 5 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 2.4 |  |  | 0 |  | 44 |  |  |  | 10 | 0 | 0 | 10 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 2.5 |  |  | 0 |  | 22 |  |  |  | 6 | 0 | 0 | 6 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 3.1 |  |  | 0 |  | 24 |  |  |  | 7 | 0 | 0 | 7 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 3.2 |  |  | 0 |  | 32 |  |  |  | 8 | 0 | 0 | 8 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 3.3 |  |  | 0 |  | 38 |  |  |  | 10 | 0 | 0 | 10 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 3.4 |  |  | 0 |  | 13 |  |  |  | 5 | 0 | 0 | 5 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 3.5 |  |  | 0 |  | 18 |  |  |  | 6 | 0 | 0 | 6 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 1.1 |  |  | 0 |  | 32 |  |  |  | 8 | 0 | 0 | 8 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 1.2 |  |  | 0 |  | 36 |  |  |  | 8 | 0 | 0 | 8 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 1.3 |  |  | 0 |  | 12 |  |  |  | 5 | 0 | 0 | 5 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 1.4 |  |  | 0 |  | 25 |  |  |  | 5 | 0 | 0 | 5 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 1.5 |  |  | 0 |  | 18 |  |  |  | 5 | 0 | 0 | 5 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 2.1 |  |  | 0 |  | 13 |  |  |  | 6 | 0 | 0 | 6 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 2.2 |  |  | 0 |  | 38 |  |  |  | 10 | 0 | 0 | 10 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 2.3 |  |  | 0 |  | 37 |  |  |  | 7 | 0 | 0 | 7 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 2.4 |  |  | 0 |  | 37 |  |  |  | 8 | 0 | 0 | 8 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 2.5 |  |  | 0 |  | 27 |  |  |  | 8 | 0 | 0 | 8 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 3.1 |  |  | 0 |  | 31 |  |  |  | 7 | 0 | 0 | 7 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 3.2 |  |  | 0 |  | 40 |  |  |  | 9 | 0 | 0 | 9 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 3.3 |  |  | 0 |  | 19 |  |  |  | 5 | 0 | 0 | 5 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 3.4 |  |  | 0 |  | 43 |  |  |  | 10 | 0 | 0 | 10 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 3.5 |  |  | 0 |  | 44 |  |  |  | 10 | 0 | 0 | 10 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 1.1 |  |  | 0 |  | 24 |  |  |  | 5 | 0 | 0 | 5 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 1.2 |  |  | 0 |  | 38 |  |  |  | 9 | 0 | 0 | 9 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 1.3 |  |  | 0 |  | 40 |  |  |  | 10 | 0 | 0 | 10 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 1.4 |  |  | 0 |  | 30 |  |  |  | 5 | 0 | 0 | 5 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 1.5 |  |  | 0 |  | 23 |  |  |  | 5 | 0 | 0 | 5 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 2.1 |  |  | 0 |  | 18 |  |  |  | 5 | 0 | 0 | 5 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 2.2 |  |  | 0 |  | 18 |  |  |  | 7 | 0 | 0 | 7 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 2.3 |  |  | 0 |  | 46 |  |  |  | 10 | 0 | 0 | 10 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 2.4 |  |  | 0 |  | 18 |  |  |  | 6 | 0 | 0 | 6 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 2.5 |  |  | 0 |  | 43 |  |  |  | 10 | 0 | 0 | 10 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 3.1 |  |  | 0 |  | 27 |  |  |  | 7 | 0 | 0 | 7 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 3.2 |  |  | 0 |  | 44 |  |  |  | 8 | 0 | 0 | 8 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 3.3 |  |  | 0 |  | 29 |  |  |  | 7 | 0 | 0 | 7 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 3.4 |  |  | 0 |  | 27 |  |  |  | 8 | 0 | 0 | 8 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 3.5 |  |  | 0 |  | 26 |  |  |  | 5 | 0 | 0 | 5 | 0 | 0
JAMP Team 1 | Sprint 1.1 |  | 0 | 5 |  |  | 5 | 5 |  | 1 | 1 | 0 | 0 | 1 | 1