## Sprint Report
Team | Sprint | State | Story Points Committed | Story Ponts Committed VC | Story Points Added | Story Points Removed | Story Points Not Completed | Story Points Completed | Story Points Completed VC | % Complete | # Issues Committed | # Issues Added | # Issues Removed | # Issues Not Completed | # Issues Completed | % Complete
JAMP Team 2 | Sprint 1.4 | CLOSED | 2 | 2 | 8 |  | 8 | 2 | 2 | 1 | 1 | 1 | 0 | 1 | 1 | 1
JAMP Team 2 | Sprint 1.5 | ACTIVE | 26 |  | 0 |  | 19 | 10 |  | 0.38462 | 5 | 0 | 0 | 3 | 2 | 0.4
JAMP Team 2 | API-JAMP Sprint 1.1 | FUTURE | 24 |  | 0 |  | 24 |  |  |  | 6 | 0 | 0 | 6 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 1.2 | FUTURE | 25 |  | 0 |  | 25 |  |  |  | 7 | 0 | 0 | 7 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 1.3 | FUTURE | 11 |  | 0 |  | 11 |  |  |  | 6 | 0 | 0 | 6 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 1.4 | FUTURE | 35 |  | 0 |  | 35 |  |  |  | 10 | 0 | 0 | 10 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 1.5 | FUTURE | 7 |  | 0 |  | 7 |  |  |  | 2 | 0 | 0 | 2 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 2.1 | FUTURE | 27 |  | 0 |  | 27 |  |  |  | 10 | 0 | 0 | 10 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 2.2 | FUTURE | 27 |  | 0 |  | 27 |  |  |  | 7 | 0 | 0 | 7 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 2.3 | FUTURE | 15 |  | 0 |  | 15 |  |  |  | 5 | 0 | 0 | 5 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 2.4 | FUTURE | 44 |  | 0 |  | 44 |  |  |  | 10 | 0 | 0 | 10 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 2.5 | FUTURE | 22 |  | 0 |  | 22 |  |  |  | 6 | 0 | 0 | 6 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 3.1 | FUTURE | 24 |  | 0 |  | 24 |  |  |  | 7 | 0 | 0 | 7 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 3.2 | FUTURE | 32 |  | 0 |  | 32 |  |  |  | 8 | 0 | 0 | 8 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 3.3 | FUTURE | 38 |  | 0 |  | 38 |  |  |  | 10 | 0 | 0 | 10 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 3.4 | FUTURE | 13 |  | 0 |  | 13 |  |  |  | 5 | 0 | 0 | 5 | 0 | 0
JAMP Team 2 | API-JAMP Sprint 3.5 | FUTURE | 18 |  | 0 |  | 18 |  |  |  | 6 | 0 | 0 | 6 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 1.1 | FUTURE | 32 |  | 0 |  | 32 |  |  |  | 8 | 0 | 0 | 8 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 1.2 | FUTURE | 36 |  | 0 |  | 36 |  |  |  | 8 | 0 | 0 | 8 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 1.3 | FUTURE | 12 |  | 0 |  | 12 |  |  |  | 5 | 0 | 0 | 5 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 1.4 | FUTURE | 25 |  | 0 |  | 25 |  |  |  | 5 | 0 | 0 | 5 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 1.5 | FUTURE | 18 |  | 0 |  | 18 |  |  |  | 5 | 0 | 0 | 5 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 2.1 | FUTURE | 13 |  | 0 |  | 13 |  |  |  | 6 | 0 | 0 | 6 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 2.2 | FUTURE | 38 |  | 0 |  | 38 |  |  |  | 10 | 0 | 0 | 10 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 2.3 | FUTURE | 37 |  | 0 |  | 37 |  |  |  | 7 | 0 | 0 | 7 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 2.4 | FUTURE | 37 |  | 0 |  | 37 |  |  |  | 8 | 0 | 0 | 8 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 2.5 | FUTURE | 27 |  | 0 |  | 27 |  |  |  | 8 | 0 | 0 | 8 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 3.1 | FUTURE | 31 |  | 0 |  | 31 |  |  |  | 7 | 0 | 0 | 7 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 3.2 | FUTURE | 40 |  | 0 |  | 40 |  |  |  | 9 | 0 | 0 | 9 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 3.3 | FUTURE | 19 |  | 0 |  | 19 |  |  |  | 5 | 0 | 0 | 5 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 3.4 | FUTURE | 43 |  | 0 |  | 43 |  |  |  | 10 | 0 | 0 | 10 | 0 | 0
JAMP Team 3 | API-JAMP Sprint 3.5 | FUTURE | 44 |  | 0 |  | 44 |  |  |  | 10 | 0 | 0 | 10 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 1.1 | FUTURE | 24 |  | 0 |  | 24 |  |  |  | 5 | 0 | 0 | 5 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 1.2 | FUTURE | 38 |  | 0 |  | 38 |  |  |  | 9 | 0 | 0 | 9 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 1.3 | FUTURE | 40 |  | 0 |  | 40 |  |  |  | 10 | 0 | 0 | 10 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 1.4 | FUTURE | 30 |  | 0 |  | 30 |  |  |  | 5 | 0 | 0 | 5 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 1.5 | FUTURE | 23 |  | 0 |  | 23 |  |  |  | 5 | 0 | 0 | 5 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 2.1 | FUTURE | 18 |  | 0 |  | 18 |  |  |  | 5 | 0 | 0 | 5 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 2.2 | FUTURE | 18 |  | 0 |  | 18 |  |  |  | 7 | 0 | 0 | 7 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 2.3 | FUTURE | 46 |  | 0 |  | 46 |  |  |  | 10 | 0 | 0 | 10 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 2.4 | FUTURE | 18 |  | 0 |  | 18 |  |  |  | 6 | 0 | 0 | 6 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 2.5 | FUTURE | 43 |  | 0 |  | 43 |  |  |  | 10 | 0 | 0 | 10 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 3.1 | FUTURE | 27 |  | 0 |  | 27 |  |  |  | 7 | 0 | 0 | 7 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 3.2 | FUTURE | 44 |  | 0 |  | 44 |  |  |  | 8 | 0 | 0 | 8 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 3.3 | FUTURE | 29 |  | 0 |  | 29 |  |  |  | 7 | 0 | 0 | 7 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 3.4 | FUTURE | 27 |  | 0 |  | 27 |  |  |  | 8 | 0 | 0 | 8 | 0 | 0
JAMP Team 4 | API-JAMP Sprint 3.5 | FUTURE | 26 |  | 0 |  | 26 |  |  |  | 5 | 0 | 0 | 5 | 0 | 0
JAMP Team 1 | Sprint 1.1 | CLOSED | 0 | 0 | 5 |  |  | 5 | 5 |  | 0 | 1 | 0 | 0 | 1
JAMP Program | Sprint 1.1 | CLOSED | 11 | 11 | 5 |  | 8 | 8 | 8 | 0.72727 | 2 | 1 | 0 | 1 | 2 | 1
JAMP Program | Sprint 1.2 | CLOSED | 8 | 8 | 8 |  | 2 | 16 | 16 | 2 | 2 | 1 | 0 | 1 | 2 | 1
JAMP Program | Sprint 1.3 | CLOSED | 10 | 10 | 6 | 11 | 3 | 2 | 2 | 0.2 | 3 | 2 | 3 | 1 | 1 | 0.33333
JAMP Program | Sprint 1.4 | CLOSED | 8 | 8 | 8 |  | 13 | 5 | 5 | 0.625 | 3 | 1 | 0 | 2 | 2 | 0.66667
JAMP Program | Sprint 1.5 | ACTIVE | 31 |  | 0 |  | 19 | 15 |  | 0.48387 | 6 | 0 | 0 | 3 | 3 | 0.5
JAMP Program | API-JAMP Sprint 1.1 | FUTURE | 80 |  | 0 |  | 80 |  |  |  | 19 | 0 | 0 | 19 | 0 | 0
JAMP Program | API-JAMP Sprint 1.2 | FUTURE | 99 |  | 0 |  | 99 |  |  |  | 24 | 0 | 0 | 24 | 0 | 0
JAMP Program | API-JAMP Sprint 1.3 | FUTURE | 63 |  | 0 |  | 63 |  |  |  | 21 | 0 | 0 | 21 | 0 | 0
JAMP Program | API-JAMP Sprint 1.4 | FUTURE | 90 |  | 0 |  | 90 |  |  |  | 20 | 0 | 0 | 20 | 0 | 0
JAMP Program | API-JAMP Sprint 1.5 | FUTURE | 48 |  | 0 |  | 48 |  |  |  | 12 | 0 | 0 | 12 | 0 | 0
JAMP Program | API-JAMP Sprint 2.1 | FUTURE | 58 |  | 0 |  | 58 |  |  |  | 21 | 0 | 0 | 21 | 0 | 0
JAMP Program | API-JAMP Sprint 2.2 | FUTURE | 83 |  | 0 |  | 83 |  |  |  | 24 | 0 | 0 | 24 | 0 | 0
JAMP Program | API-JAMP Sprint 2.3 | FUTURE | 98 |  | 0 |  | 98 |  |  |  | 22 | 0 | 0 | 22 | 0 | 0
JAMP Program | API-JAMP Sprint 2.4 | FUTURE | 99 |  | 0 |  | 99 |  |  |  | 24 | 0 | 0 | 24 | 0 | 0
JAMP Program | API-JAMP Sprint 2.5 | FUTURE | 92 |  | 0 |  | 92 |  |  |  | 24 | 0 | 0 | 24 | 0 | 0
JAMP Program | API-JAMP Sprint 3.1 | FUTURE | 82 |  | 0 |  | 82 |  |  |  | 21 | 0 | 0 | 21 | 0 | 0
JAMP Program | API-JAMP Sprint 3.2 | FUTURE | 116 |  | 0 |  | 116 |  |  |  | 25 | 0 | 0 | 25 | 0 | 0
JAMP Program | API-JAMP Sprint 3.3 | FUTURE | 86 |  | 0 |  | 86 |  |  |  | 22 | 0 | 0 | 22 | 0 | 0
JAMP Program | API-JAMP Sprint 3.4 | FUTURE | 83 |  | 0 |  | 83 |  |  |  | 23 | 0 | 0 | 23 | 0 | 0
JAMP Program | API-JAMP Sprint 3.5 | FUTURE | 88 |  | 0 |  | 88 |  |  |  | 21 | 0 | 0 | 21 | 0 | 0