## Sheet1
Row Labels | Sum of Story Points Committed | Sum of Story Points Completed
2020 Sprint 12 - Team 42 |  | 5
Sprint 0 (IDAP 2020) | 35 | 30
Sprint 1 (IDAP 2021) | 39 | 39
Sprint 10 (IDAP 2020) |  | 34
Sprint 10 (IDAP 2021) | 13
Sprint 11 (IDAP 2020) |  | 23
Sprint 11 (IDAP 2021) | 8
Sprint 12 (IDAP 2021) | 8
Sprint 13 (IDAP 2020) |  | 28
Sprint 13 (IDAP 2021) | 8
Sprint 14 (IDAP 2020) | 45 | 27
Sprint 14 (IDAP 2021) | 0
Sprint 15 (IDAP 2020) | 48 | 19
Sprint 15 (IDAP 2021) | 0
Sprint 16 (IDAP 2020) | 29 | 5
Sprint 16 (IDAP 2021) | 0
Sprint 17 (IDAP 2020) |  | 25
Sprint 17 (IDAP 2021) | 0
Sprint 18 (IDAP 2020) |  | 24
Sprint 18 (IDAP 2021) | 0
Sprint 19 (IDAP 2020) |  | 22
Sprint 19 (IDAP 2021) | 0
Sprint 2 (IDAP 2021) |  | 35
Sprint 20 (IDAP 2020) | 26 | 23
Sprint 20 (IDAP 2021) | 0
Sprint 21 (IDAP 2020) | 24 | 25
Sprint 21 (IDAP 2021) | 0
Sprint 22 (IDAP 2020) | 23 | 23
Sprint 22 (IDAP 2021) | 0
Sprint 23 (IDAP 2020) | 37 | 40
Sprint 23 (IDAP 2021) | 0
Sprint 24 (IDAP 2020) |  | 37
Sprint 24 (IDAP 2021) | 0
Sprint 25 (IDAP 2020) |  | 31
Sprint 25 (IDAP 2021) | 0
Sprint 26 (IDAP 2020) |  | 38
Sprint 26 (IDAP 2021) | 0
Sprint 3 (IDAP 2021) | 43 | 44
Sprint 4 (IDAP 2021) |  | 53
Sprint 5 (IDAP 2020) |  | 8
Sprint 5 (IDAP 2021) |  | 70
Sprint 6 (IDAP 2020)
Sprint 6 (IDAP 2021) | 68 | 68
Sprint 7 (IDAP 2020) |  | 16
Sprint 7 (IDAP 2021) |  | 16
Sprint 8 (IDAP 2020) |  | 18
Sprint 8 (IDAP 2021) | 59
Sprint 9 (IDAP 2020) |  | 20
Sprint 9 (IDAP 2021) | 62
Grand Total | 575 | 846

## Sprint Report
Team | Sprint | Story Points Committed | Story Ponts Committed VC | Story Points Added | Story Points Removed | Story Points Not Completed | Story Points Completed | Story Points Completed VC | % Complete | # Issues Committed | # Issues Added | # Issues Removed | # Issues Not Completed | # Issues Completed | % Complete
IDAP Scrum Board (AbracaData) | Sprint 5 (IDAP 2020) |  |  | 16 | 30 | 8 | 8 |  |  | 8 | 13 | 10 | 3 | 8 | 1
IDAP Scrum Board (AbracaData) | Sprint 0 (IDAP 2020) | 35 |  | 8 | 21 |  | 30 |  | 0.85714 | 10 | 1 | 4 | 0 | 7 | 0.7
IDAP Scrum Board (AbracaData) | Sprint 6 (IDAP 2020) |  |  | 0 | 16 | 8 |  |  |  | 7 | 2 | 5 | 1 | 3 | 0.42857
IDAP Scrum Board (AbracaData) | Sprint 7 (IDAP 2020) |  |  | 3 | 21 |  | 16 |  |  | 8 | 2 | 7 | 0 | 3 | 0.375
IDAP Scrum Board (AbracaData) | Sprint 8 (IDAP 2020) |  |  | 0 |  | 10 | 18 |  |  | 9 | 1 | 2 | 3 | 5 | 0.55556
IDAP Scrum Board (AbracaData) | Sprint 9 (IDAP 2020) |  |  | 0 | 13 |  | 20 |  |  | 11 | 2 | 5 | 0 | 8 | 0.72727
IDAP Scrum Board (AbracaData) | Sprint 10 (IDAP 2020) |  |  | 0 |  |  | 34 |  |  | 11 | 1 | 3 | 1 | 8 | 0.72727
IDAP Scrum Board (AbracaData) | Sprint 11 (IDAP 2020) |  |  | 0 | 5 |  | 23 |  |  | 9 | 1 | 4 | 0 | 6 | 0.66667
IDAP Scrum Board (AbracaData) | 2020 Sprint 12 - Team 42 |  |  | 0 | 1 | 26 | 5 |  |  | 6 | 2 | 1 | 5 | 2 | 0.33333
IDAP Scrum Board (AbracaData) | Sprint 13 (IDAP 2020) |  |  | 10 | 13 |  | 28 |  |  | 5 | 4 | 3 | 0 | 6 | 1.2
IDAP Scrum Board (AbracaData) | Sprint 14 (IDAP 2020) | 45 |  | 0 | 16 |  | 27 |  | 0.6 | 10 | 0 | 3 | 0 | 7 | 0.7
IDAP Scrum Board (AbracaData) | Sprint 15 (IDAP 2020) | 48 |  | 0 | 13 |  | 19 |  | 0.39583 | 9 | 0 | 4 | 0 | 5 | 0.55556
IDAP Scrum Board (AbracaData) | Sprint 16 (IDAP 2020) | 29 |  | 0 | 13 |  | 5 |  | 0.17241 | 5 | 0 | 4 | 0 | 1 | 0.2
IDAP Scrum Board (AbracaData) | Sprint 17 (IDAP 2020) |  |  | 11 | 8 |  | 25 |  |  | 6 | 4 | 3 | 0 | 7 | 1.1667
IDAP Scrum Board (AbracaData) | Sprint 18 (IDAP 2020) |  |  | 20 | 11 |  | 24 |  |  | 10 | 10 | 7 | 0 | 13 | 1.3
IDAP Scrum Board (AbracaData) | Sprint 19 (IDAP 2020) |  |  | 5 | 6 | 5 | 22 |  |  | 9 | 3 | 3 | 1 | 8 | 0.88889
IDAP Scrum Board (AbracaData) | Sprint 20 (IDAP 2020) | 26 |  | 0 |  | 3 | 23 |  | 0.88462 | 10 | 1 | 0 | 2 | 9 | 0.9
IDAP Scrum Board (AbracaData) | Sprint 21 (IDAP 2020) | 24 |  | 1 |  |  | 25 |  | 1.0417 | 11 | 1 | 0 | 3 | 9 | 0.81818
IDAP Scrum Board (AbracaData) | Sprint 22 (IDAP 2020) | 23 |  | 0 |  |  | 23 |  | 1 | 9 | 0 | 0 | 2 | 7 | 0.77778
IDAP Scrum Board (AbracaData) | Sprint 23 (IDAP 2020) | 37 |  | 3 |  |  | 40 |  | 1.0811 | 11 | 1 | 0 | 1 | 11 | 1
IDAP Scrum Board (AbracaData) | Sprint 24 (IDAP 2020) |  |  | 0 |  |  | 37 |  |  | 9 | 1 | 1 | 1 | 8 | 0.88889
IDAP Scrum Board (AbracaData) | Sprint 25 (IDAP 2020) |  |  | 0 |  | 8 | 31 |  |  | 10 | 4 | 1 | 1 | 12 | 1.2
IDAP Scrum Board (AbracaData) | Sprint 26 (IDAP 2020) |  | 38 | 0 |  |  | 38 | 38 |  | 6 | 3 | 0 | 1 | 8 | 1.3333
IDAP Scrum Board (AbracaData) | Sprint 1 (IDAP 2021) | 39 | 39 | 0 |  |  | 39 | 39 | 1 | 7 | 0 | 0 | 0 | 7 | 1
IDAP Scrum Board (AbracaData) | Sprint 2 (IDAP 2021) |  | 35 | 0 |  |  | 35 | 35 |  | 8 | 1 | 0 | 2 | 7 | 0.875
IDAP Scrum Board (AbracaData) | Sprint 3 (IDAP 2021) | 43 | 46 | 8 | 7 | 5 | 44 | 44 | 1.0233 | 11 | 2 | 2 | 2 | 9 | 0.81818
IDAP Scrum Board (AbracaData) | Sprint 4 (IDAP 2021) |  | 56 | 8 |  | 8 | 53 | 53 |  | 14 | 1 | 0 | 4 | 11 | 0.78571
IDAP Scrum Board (AbracaData) | Sprint 5 (IDAP 2021) |  | 80 | 0 | 2 |  | 70 | 70 |  | 19 | 1 | 1 | 3 | 16 | 0.84211
IDAP Scrum Board (AbracaData) | Sprint 6 (IDAP 2021) | 68 | 89 | 0 |  |  | 68 | 68 | 1 | 17 | 0 | 0 | 5 | 12 | 0.70588
IDAP Scrum Board (AbracaData) | Sprint 7 (IDAP 2021) |  |  | 0 |  | 58 | 16 |  |  | 18 | 1 | 0 | 15 | 4 | 0.22222
IDAP Scrum Board (AbracaData) | Sprint 8 (IDAP 2021) | 59 |  | 0 |  | 59 |  |  |  | 15 | 0 | 0 | 15 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 9 (IDAP 2021) | 62 |  | 0 |  | 62 |  |  |  | 12 | 0 | 0 | 12 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 10 (IDAP 2021) | 13 |  | 0 |  | 13 |  |  |  | 4 | 0 | 0 | 4 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 11 (IDAP 2021) | 8 |  | 0 |  | 8 |  |  |  | 1 | 0 | 0 | 1 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 12 (IDAP 2021) | 8 |  | 0 |  | 8 |  |  |  | 1 | 0 | 0 | 1 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 13 (IDAP 2021) | 8 |  | 0 |  | 8 |  |  |  | 1 | 0 | 0 | 1 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 14 (IDAP 2021) | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 15 (IDAP 2021) | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 16 (IDAP 2021) | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 17 (IDAP 2021) | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 18 (IDAP 2021) | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 19 (IDAP 2021) | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 20 (IDAP 2021) | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 21 (IDAP 2021) | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 22 (IDAP 2021) | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 23 (IDAP 2021) | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 24 (IDAP 2021) | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 25 (IDAP 2021) | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 26 (IDAP 2021) | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0