## Sprint Report
Team | Sprint | Story Points Committed | Story Ponts Committed VC | Story Points Added | Story Points Removed | Story Points Not Completed | Story Points Completed | Story Points Completed VC | % Complete | # Issues Committed | # Issues Added | # Issues Removed | # Issues Not Completed | # Issues Completed | % Complete2
13 sprint board | Base Platform Sprint 37 |  |  | 0 | [5 empty] | 1 | 1 | 0 | 0 | 1 | 100%
13 sprint board | Base Platform Sprint 40 |  |  | 0 | [5 empty] | 1 | 1 | 0 | 0 | 1 | 100%
13 sprint board | MRR- Sprint 35 |  |  | 2 |  |  | 57.5 |  |  | 31 | 2 | 0 | 3 | 28 | 90.32%
13 sprint board | MRR- Sprint 36 |  |  | 3.5 | 10 | 3.5 | 25.5 |  |  | 20 | 8 | 6 | 7 | 13 | 65%
13 sprint board | MRR- Sprint 37 |  |  | 8 | 3 |  | 53.5 |  |  | 56 | 41 | 1 | 0 | 56 | 100%
13 sprint board | MRR- Sprint 38 |  |  | 18 | 13 | 33 | 46.5 |  |  | 49 | 17 | 10 | 12 | 37 | 75.51%
13 sprint board | MRR- Sprint 39 |  |  | 33.5 |  | 25.5 | 61.5 |  |  | 50 | 20 | 1 | 10 | 40 | 80%
13 sprint board | MRR- Sprint 40 |  |  | 47.5 | 7.5 | 26 | 70.5 |  |  | 37 | 22 | 5 | 8 | 29 | 78.38%
13 sprint board | MRR- Sprint 41 |  |  | 48 | 2 | 11.5 | 80.5 |  |  | 47 | 20 | 3 | 6 | 41 | 87.23%
13 sprint board | MRR- Sprint 42 |  |  | 11.5 | 5 | 10 | 77.5 |  |  | 52 | 18 | 9 | 6 | 46 | 88.46%
13 sprint board | MRR- Sprint 43 |  |  | 9 | 5 |  | 96.5 |  |  | 55 | 16 | 2 | 0 | 55 | 100%
13 sprint board | MRR- Sprint 44 |  |  | 6 |  | 21 | 57 |  |  | 51 | 19 | 0 | 8 | 43 | 84.31%
13 sprint board | MRR- Sprint 45 |  |  | 23 | 10 |  | 99 |  |  | 45 | 19 | 6 | 3 | 42 | 93.33%
13 sprint board | MRR- Sprint 46 |  |  | 30 | 6 | 18 | 74 |  |  | 51 | 19 | 17 | 8 | 43 | 84.31%
13 sprint board | MRR- Sprint 47 |  |  | 31 | 4 | 8 | 83.5 |  |  | 68 | 43 | 6 | 9 | 59 | 86.76%
13 sprint board | PK Sprint 6 |  |  | 0 | [5 empty] | 1 | 8 | 2 | 0 | 1 | 100%
13 sprint board | PK Sprint 8 |  |  | 0 | [5 empty] | 1 | 2 | 1 | 0 | 1 | 100%
13 sprint board | Retrieval Kanban |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
13 sprint board | Sprint 10 |  |  | 0 | [5 empty] | 10 | 7 | 20 | 0 | 10 | 100%
13 sprint board | Sprint 11 |  |  | 0 | [5 empty] | 3 | 17 | 27 | 0 | 3 | 100%
13 sprint board | Sprint 12 |  |  | 0 | [5 empty] | 29 | 27 | 22 | 0 | 29 | 100%
13 sprint board | Sprint 13 |  |  | 0 | [5 empty] | 49 | 26 | 24 | 0 | 49 | 100%
13 sprint board | Sprint 14 |  |  | 0 | [5 empty] | 40 | 20 | 14 | 0 | 40 | 100%
13 sprint board | Sprint 15 |  |  | 8 | [5 empty] | 29 | 34 | 15 | 0 | 29 | 100%
13 sprint board | Sprint 16 |  |  | 8 | [5 empty] | 12 | 10 | 8 | 0 | 12 | 100%
13 sprint board | Sprint 17 |  |  | 0 | [5 empty] | 38 | 9 | 3 | 0 | 38 | 100%
13 sprint board | Sprint 18 |  |  | 0 | [5 empty] | 14 | 10 | 10 | 0 | 14 | 100%
13 sprint board | Sprint 19 |  |  | 0 | [5 empty] | 10 | 22 | 11 | 0 | 10 | 100%
13 sprint board | Sprint 2 |  |  | 0 |  |  | 21 |  |  | 2 | 0 | 2 | 0 | 2 | 100%
13 sprint board | Sprint 20 |  |  | 0 | [5 empty] | 13 | 6 | 17 | 0 | 13 | 100%
13 sprint board | Sprint 21 |  |  | 0 | [5 empty] | 17 | 13 | 10 | 0 | 17 | 100%
13 sprint board | Sprint 22 |  |  | 0 | [5 empty] | 36 | 38 | 7 | 0 | 36 | 100%
13 sprint board | Sprint 23 |  |  | 0 | [5 empty] | 33 | 22 | 9 | 0 | 33 | 100%
13 sprint board | Sprint 24 |  |  | 0 | [5 empty] | 19 | 18 | 17 | 0 | 19 | 100%
13 sprint board | Sprint 25 |  |  | 0 | 3 |  |  |  |  | 19 | 7 | 25 | 0 | 19 | 100%
13 sprint board | Sprint 26 |  |  | 0 | 10 |  |  |  |  | 0 | 5 | 27 | 0 | 0
13 sprint board | Sprint 27 |  |  | 0 | 8 |  | 1 |  |  | 1 | 1 | 12 | 0 | 1 | 100%
13 sprint board | Sprint 28 |  |  | 1 | 6 |  | 4 |  |  | 12 | 8 | 6 | 0 | 12 | 100%
13 sprint board | Sprint 29 |  |  | 3 |  | 29 | 3 |  |  | 14 | 3 | 1 | 11 | 3 | 21.43%
13 sprint board | Sprint 3 |  |  | 0 |  |  | 23 |  |  | 4 | 0 | 1 | 0 | 4 | 100%
13 sprint board | Sprint 30 |  |  | 31 | 3 | 9 | 28.5 |  |  | 18 | 12 | 2 | 4 | 14 | 77.78%
13 sprint board | Sprint 31 |  |  | 33.5 |  | 6 | 27.5 |  |  | 19 | 22 | 1 | 5 | 14 | 73.68%
13 sprint board | Sprint 32 |  |  | 0.5 | 8 | 3 | 20.5 |  |  | 14 | 1 | 1 | 1 | 13 | 92.86%
13 sprint board | Sprint 33 |  |  | 13 |  | 16 | 8 |  |  | 24 | 14 | 0 | 5 | 19 | 79.17%
13 sprint board | Sprint 34 |  |  | 13.5 | 3 | 11.5 | 22 |  |  | 28 | 9 | 1 | 11 | 17 | 60.71%
13 sprint board | Sprint 4 |  |  | 0 | [5 empty] | 9 | 3 | 5 | 0 | 9 | 100%
13 sprint board | Sprint 6 |  |  | 0 | [5 empty] | 7 | 11 | 13 | 0 | 7 | 100%
13 sprint board | Sprint 7 |  |  | 0 | [5 empty] | 10 | 15 | 6 | 0 | 10 | 100%
13 sprint board | Sprint 8 |  |  | 0 | [5 empty] | 9 | 10 | 5 | 0 | 9 | 100%
13 sprint board | Sprint 9 |  |  | 0 | [5 empty] | 12 | 20 | 14 | 0 | 12 | 100%
Base Platform- ACO Backlog Board | 2017 BP Sprint 12 |  |  | 3 |  | 74 | 3 |  |  | 22 | 6 | 1 | 21 | 1 | 4.545%
Base Platform- ACO Backlog Board | 2017 BP Sprint 13 |  |  | 77 |  | 15 | 54 |  |  | 20 | 22 | 4 | 5 | 15 | 75%
Base Platform- ACO Backlog Board | 2017 BP Sprint 14 |  |  | 0 |  |  | 23 |  |  | 27 | 13 | 1 | 2 | 25 | 92.59%
Base Platform- ACO Backlog Board | 2017 BP Sprint 15 |  |  | 8 | 8 | 11 | 5 |  |  | 8 | 5 | 3 | 3 | 5 | 62.5%
Base Platform- ACO Backlog Board | 2017 BP Sprint 16 |  |  | 0 | 6 |  | 24 |  |  | 18 | 6 | 2 | 2 | 16 | 88.89%
Base Platform- ACO Backlog Board | 2017 BP Sprint 17 |  |  | 3 |  | 5 | 11 |  |  | 9 | 3 | 1 | 2 | 7 | 77.78%
Base Platform- ACO Backlog Board | 2017 BP Sprint 18 | 10 |  | 5 |  | 5 | 13 |  | 130% | 6 | 1 | 2 | 1 | 5 | 83.33%
Base Platform- ACO Backlog Board | 2017 BP Sprint 19 |  |  | 0 |  |  | 12 |  |  | 4 | 0 | 2 | 0 | 4 | 100%
Base Platform- ACO Backlog Board | 2017 BP Sprint 20 |  |  | 3 |  |  | 3 |  |  | 15 | 8 | 3 | 3 | 12 | 80%
Base Platform- ACO Backlog Board | 2017 BP Sprint 21 |  |  | 0 | [5 empty] | 3 | 1 | 0 | 1 | 2 | 66.67%
Base Platform- ACO Backlog Board | 2017 BP Sprint 22 |  | 0 | 0 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2 | 100%
Base Platform- ACO Backlog Board | 2018 BP Sprint 2 |  | 0 | 0 |  |  |  | 0 |  | 7 | 0 | 0 | 0 | 7 | 100%
Base Platform- ACO Backlog Board | Base Platform Sprint 37 |  |  | 0 |  |  | 10 |  |  | 5 | 0 | 1 | 0 | 5 | 100%
Base Platform- ACO Backlog Board | Base Platform Sprint 38 |  |  | 2 | 2 | 5 |  |  |  | 3 | 1 | 3 | 3 | 0 | 0%
Base Platform- ACO Backlog Board | Base Platform Sprint 39 |  |  | 5 |  | 4 | 5 |  |  | 8 | 7 | 1 | 2 | 6 | 75%
Base Platform- ACO Backlog Board | Base Platform Sprint 40 | 2 |  | 4 | 3 | 4 | 2 |  | 100% | 4 | 2 | 3 | 2 | 2 | 50%
Base Platform- ACO Backlog Board | Base Platform Sprint 41 |  |  | 4 |  | 3 | 5 |  |  | 5 | 3 | 24 | 2 | 3 | 60%
Base Platform- ACO Backlog Board | Base Platform Sprint 42 |  |  | 1 | 5 | 5 | 1 |  |  | 3 | 1 | 1 | 1 | 2 | 66.67%
Base Platform- ACO Backlog Board | Base Platform Sprint 43 |  |  | 0 | 13 |  | 4 |  |  | 2 | 0 | 3 | 0 | 2 | 100%
Base Platform- ACO Backlog Board | Base Platform Sprint 47 |  |  | 0 |  | 38 | 8 |  |  | 16 | 3 | 1 | 10 | 6 | 37.5%
Base Platform- ACO Backlog Board | Base Platform Sprint 48 |  |  | 2 |  | 3 | 2 |  |  | 12 | 4 | 2 | 5 | 7 | 58.33%
Base Platform- ACO Backlog Board | MRR- Sprint 38 |  |  | 0 | [5 empty] | 1 | 0 | 0 | 1 | 0 | 0%
Base Platform- ACO Backlog Board | PK Sprint 10 |  |  | 0 | [5 empty] | 17 | 28 | 10 | 0 | 17 | 100%
Base Platform- ACO Backlog Board | PK Sprint 11 |  |  | 0 | [5 empty] | 9 | 9 | 13 | 0 | 9 | 100%
Base Platform- ACO Backlog Board | PK Sprint 12 |  |  | 0 | [5 empty] | 8 | 5 | 9 | 0 | 8 | 100%
Base Platform- ACO Backlog Board | PK Sprint 13 |  |  | 0 | [5 empty] | 2 | 2 | 9 | 0 | 2 | 100%
Base Platform- ACO Backlog Board | PK Sprint 6 |  |  | 0 | [5 empty] | 1 | 2 | 1 | 0 | 1 | 100%
Base Platform- ACO Backlog Board | PK Sprint 7 |  |  | 0 | [5 empty] | 1 | 2 | 1 | 0 | 1 | 100%
Base Platform- ACO Backlog Board | PK Sprint 8 |  |  | 0 | [5 empty] | 5 | 15 | 10 | 0 | 5 | 100%
Base Platform- ACO Backlog Board | PK Sprint 9 |  |  | 0 | [5 empty] | 3 | 12 | 9 | 0 | 3 | 100%
Base Platform- ACO Backlog Board | Sprint 1 |  |  | 0 | [5 empty] | 4 | 0 | 1 | 0 | 4 | 100%
Base Platform- ACO Backlog Board | Sprint 20 |  |  | 0 | [5 empty] | 0 | 4 | 0 | 0 | 0
Base Platform- ACO Backlog Board | Sprint 25 |  |  | 0 | [5 empty] | 1 | 1 | 0 | 0 | 1 | 100%
Base Platform- ACO Backlog Board | Sprint 26 |  |  | 1 | 1 |  |  |  |  | 1 | 2 | 1 | 0 | 1 | 100%
Base Platform- ACO Backlog Board | Sprint 28 |  |  | 0 | [5 empty] | 2 | 0 | 4 | 0 | 2 | 100%
Base Platform- ACO Backlog Board | Sprint 29 |  |  | 0 |  |  | 13 |  |  | 4 | 1 | 0 | 0 | 4 | 100%
Base Platform- ACO Backlog Board | Sprint 30 |  |  | 0 | [5 empty] | 1 | 0 | 0 | 0 | 1 | 100%
Base Platform- ACO Backlog Board | Sprint 31 |  |  | 0 |  | 4 |  |  |  | 2 | 0 | 0 | 2 | 0 | 0%
Base Platform- ACO Backlog Board | Sprint 32 |  |  | 3 |  |  | 5 |  |  | 4 | 1 | 0 | 1 | 3 | 75%
Base Platform- ACO Backlog Board | Sprint 34 |  |  | 0 |  |  | 3 |  |  | 1 | 0 | 0 | 0 | 1 | 100%
Base Platform- ACO Backlog Board | Sprint 7 |  |  | 0 | [5 empty] | 0 | 7 | 0 | 0 | 0
Base Platform- ACO Backlog Board | Team Raider Sprint 14 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2017 BP Sprint 12 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2017 BP Sprint 13 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2017 BP Sprint 14 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2017 BP Sprint 15 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2017 BP Sprint 16 |  |  | 0 |  |  | 5 |  |  | 1 | 0 | 0 | 0 | 1 | 100%
Bass Platform Sprint Board | 2017 BP Sprint 17 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2017 BP Sprint 18 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2017 BP Sprint 19 |  |  | 0 |  |  | 5 |  |  | 1 | 0 | 0 | 0 | 1 | 100%
Bass Platform Sprint Board | 2017 BP Sprint 20 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2017 BP Sprint 21 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2017 BP Sprint 22 |  |  | 0 |  |  | 3 |  |  | 1 | 0 | 0 | 0 | 1 | 100%
Bass Platform Sprint Board | 2017 BP Sprint 23 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2017 BP Sprint 24 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2017 BP Sprint 25 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2017 BP Sprint 26 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2018 BP Sprint 1 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2018 BP Sprint 10 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2018 BP Sprint 11 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2018 BP Sprint 12 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2018 BP Sprint 13 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2018 BP Sprint 14 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2018 BP Sprint 15 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2018 BP Sprint 16 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2018 BP Sprint 17 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2018 BP Sprint 18 |  |  | 0 |  |  | 8 |  |  | 1 | 0 | 0 | 0 | 1 | 100%
Bass Platform Sprint Board | 2018 BP Sprint 19 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2018 BP Sprint 2 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2018 BP Sprint 20 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2018 BP Sprint 21 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2018 BP Sprint 22 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2018 BP Sprint 25 | 5 |  | 2 |  | 5 | 2 |  | 40% | 2 | 1 | 0 | 1 | 1 | 50%
Bass Platform Sprint Board | 2018 BP Sprint 3 |  |  | 3 | 3 |  |  |  |  | 0 | 1 | 1 | 0 | 0
Bass Platform Sprint Board | 2018 BP Sprint 4 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2018 BP Sprint 5 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2018 BP Sprint 6 | 11 |  | 0 |  | 3 | 8 |  | 72.73% | 2 | 0 | 0 | 1 | 1 | 50%
Bass Platform Sprint Board | 2018 BP Sprint 7 |  |  | 0 |  |  | 3 |  |  | 1 | 0 | 0 | 0 | 1 | 100%
Bass Platform Sprint Board | 2018 BP Sprint 8 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | 2018 BP Sprint 9 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | Base Platform Sprint 37 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | Base Platform Sprint 38 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | Base Platform Sprint 39 |  |  | 0 |  | 10 |  |  |  | 1 | 0 | 0 | 1 | 0 | 0%
Bass Platform Sprint Board | Base Platform Sprint 40 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | Base Platform Sprint 41 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | Base Platform Sprint 42 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | Base Platform Sprint 43 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | Base Platform Sprint 47 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | Base Platform Sprint 48 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | Sprint 1 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | Sprint 33 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Bass Platform Sprint Board | Sprint 34 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
BI/Data Mart C.I. Projects | 2018 Sprint 10 Trendy Outliers |  |  | 2 | 2 |  | 4 |  |  | 2 | 1 | 1 | 0 | 2 | 100%
BI/Data Mart C.I. Projects | 2018 Sprint 11 BI & Reporting |  |  | 0 | 6 |  |  |  |  | 0 | 0 | 2 | 0 | 0
BI/Data Mart C.I. Projects | 2018 Sprint 12 - Team 42 |  |  | 3 | 3 | 12 |  |  |  | 4 | 1 | 1 | 4 | 0 | 0%
BI/Data Mart C.I. Projects | 2018 Sprint 14 - Team 42 |  |  | 0 | 15 |  | 1 |  |  | 1 | 0 | 5 | 0 | 1 | 100%
BI/Data Mart C.I. Projects | 2018 Sprint 15 - Team 42 |  |  | 5 | 6 |  |  |  |  | 0 | 2 | 3 | 0 | 0
BI/Data Mart C.I. Projects | 2018 Sprint 16 - Team 42 |  |  | 0 | 8 | 8 |  |  |  | 1 | 0 | 3 | 1 | 0 | 0%
BI/Data Mart C.I. Projects | 2018 Sprint 17 - Team 42 |  |  | 8 | 21 |  |  |  |  | 0 | 1 | 6 | 0 | 0
BI/Data Mart C.I. Projects | 2018 Sprint 19 - Team 42 |  |  | 0 | 12 |  |  |  |  | 0 | 0 | 4 | 0 | 0
BI/Data Mart C.I. Projects | 2018 Sprint 20 - Team 42 |  |  | 0 |  | 3 |  |  |  | 1 | 0 | 0 | 1 | 0 | 0%
BI/Data Mart C.I. Projects | 2018 Sprint 21 - Team 42 |  |  | 0 | 10 |  | 6 |  |  | 2 | 0 | 2 | 0 | 2 | 100%
BI/Data Mart C.I. Projects | 2018 Sprint 22 - Team 42 |  |  | 0 | 1 | 6 |  |  |  | 2 | 0 | 1 | 2 | 0 | 0%
BI/Data Mart C.I. Projects | 2018 Sprint 23 - Team 42 |  |  | 0 | 11 | 3 |  |  |  | 1 | 0 | 3 | 1 | 0 | 0%
BI/Data Mart C.I. Projects | 2018 Sprint 24 - Team 42 |  | 7 | 0 | 7 |  |  | 0 |  | 0 | 0 | 3 | 0 | 0
BI/Data Mart C.I. Projects | 2018 Sprint 26 - Team 42 |  | 3 | 0 | 3 |  |  | 0 |  | 0 | 0 | 1 | 0 | 0
BI/Data Mart C.I. Projects | 2018 Sprint 3 TrendyOutliers |  |  | 2 |  |  | 2 |  |  | 1 | 1 | 0 | 0 | 1 | 100%
BI/Data Mart C.I. Projects | 2018 Sprint 4 TrendyOutliers |  |  | 2 |  |  | 2 |  |  | 1 | 1 | 0 | 0 | 1 | 100%
BI/Data Mart C.I. Projects | 2018 Sprint 6 TrendyOutliers |  |  | 1 |  |  | 3 |  |  | 2 | 1 | 0 | 0 | 2 | 100%
BI/Data Mart C.I. Projects | 2018 Sprint 9 Trendy Outliers |  |  | 0 |  | 5 |  |  |  | 1 | 0 | 0 | 1 | 0 | 0%
BI/Data Mart C.I. Projects | 2019 Sprint 12 - Team 42 |  | 9 | 0 | 3 | 6 |  | 0 |  | 2 | 0 | 1 | 2 | 0 | 0%
BI/Data Mart C.I. Projects | 2019 Sprint 13 - Team 42 |  | 6 | 0 |  | 6 |  | 0 |  | 2 | 0 | 0 | 2 | 0 | 0%
BI/Data Mart C.I. Projects | 2020 Sprint 3 - Team 42 |  | 8 | 0 | 8 |  |  | 0 |  | 0 | 0 | 1 | 0 | 0
BI/Data Mart C.I. Projects | BI-SHFB 2018 - Sprint 10 | 14 |  | 0 | 3 | 11 | 3 |  | 21.43% | 3 | 0 | 1 | 2 | 1 | 33.33%
BI/Data Mart C.I. Projects | BI-SHFB 2018 - Sprint 6 |  |  | 0 |  | 5 |  |  |  | 1 | 0 | 0 | 1 | 0 | 0%
BI/Data Mart C.I. Projects | BI-SHFB 2018 - Sprint 7 | 8 |  | 0 |  | 3 | 5 |  | 62.5% | 2 | 0 | 0 | 1 | 1 | 50%
BI/Data Mart C.I. Projects | BI-SHFB 2018 - Sprint 8 |  |  | 0 | 3 | 8 |  |  |  | 2 | 1 | 1 | 1 | 1 | 50%
BI/Data Mart C.I. Projects | BI-SHFB 2018 - Sprint 9 | 14 |  | 0 |  | 14 |  |  |  | 4 | 1 | 0 | 3 | 1 | 25%
BI/Data Mart C.I. Projects | BI: Team 42 - Sprint 14 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
BI/Data Mart Consolidated | 2018 Sprint 3 TrendyOutliers |  |  | 28 |  | 7 | 16 |  |  | 10 | 10 | 0 | 4 | 6 | 60%
BI/Data Mart Consolidated | 2018 Sprint 4 TrendyOutliers | 7 |  | 34 |  | 7 | 31 |  | 442.9% | 11 | 10 | 1 | 2 | 9 | 81.82%
BI/Data Mart Consolidated | BI 2017 - Sprint 13 |  |  | 0 |  |  | 28 |  |  | 23 | 0 | 0 | 8 | 15 | 65.22%
BI/Data Mart Consolidated | BI 2017 - Sprint 14 |  |  | 3 | 3 | 8 | 32 |  |  | 26 | 4 | 1 | 8 | 18 | 69.23%
BI/Data Mart Consolidated | BI 2017 - Sprint 15 |  |  | 6.5 |  |  | 44.5 |  |  | 34 | 9 | 0 | 7 | 27 | 79.41%
BI/Data Mart Consolidated | BI 2017 - Sprint 16 |  |  | 4 |  | 3 | 38 |  |  | 26 | 3 | 0 | 8 | 18 | 69.23%
BI/Data Mart Consolidated | BI 2017 - Sprint 17 |  |  | 2 |  | 3 | 30 |  |  | 34 | 9 | 0 | 4 | 30 | 88.24%
BI/Data Mart Consolidated | BI Release 2 - Sprint 0 |  |  | 0 |  | 3 |  |  |  | 14 | 3 | 0 | 7 | 7 | 50%
BI/Data Mart Consolidated | BI Release 2 - Sprint 1 |  |  | 0 | 8 |  | 15 |  |  | 9 | 0 | 1 | 0 | 9 | 100%
BI/Data Mart Consolidated | BI Release 2 - Sprint 2 | 45 |  | 0 | 8 | 8 | 37 |  | 82.22% | 7 | 0 | 1 | 3 | 4 | 57.14%
BI/Data Mart Consolidated | BI Release 2 - Sprint 3 | 35 |  | 0 | 8 | 8 | 27 |  | 77.14% | 9 | 0 | 2 | 2 | 7 | 77.78%
BI/Data Mart Consolidated | BI Release 2 - Sprint 4 |  |  | 0 |  |  | 35 |  |  | 16 | 1 | 0 | 1 | 15 | 93.75%
BI/Data Mart Consolidated | BI Release 2 - Sprint 5 | 24 |  | 8 | 3 |  | 28 |  | 116.7% | 16 | 3 | 1 | 2 | 14 | 87.5%
BI/Data Mart Consolidated | BI Release 2 - Sprint 6 |  |  | 9 |  | 8 | 42 |  |  | 27 | 6 | 0 | 2 | 25 | 92.59%
BI/Data Mart Consolidated | BI Sprint 0 |  |  | 5 | 3 |  |  |  |  | 2 | 1 | 1 | 2 | 0 | 0%
BI/Data Mart Consolidated | BI Sprint 1 |  |  | 0 |  |  | 7 |  |  | 4 | 0 | 0 | 2 | 2 | 50%
BI/Data Mart Consolidated | BI Sprint 2 |  |  | 38 |  | 10 | 38 |  |  | 15 | 9 | 0 | 3 | 12 | 80%
BI/Data Mart Consolidated | BI Sprint 3 |  |  | 3 |  | 20 | 25 |  |  | 13 | 2 | 0 | 4 | 9 | 69.23%
BI/Data Mart Consolidated | BI Sprint 4 | 51 |  | 5 |  | 33 | 23 |  | 45.1% | 10 | 1 | 0 | 4 | 6 | 60%
BI/Data Mart Consolidated | BI Sprint 5 | 28 |  | 0 |  | 23 | 5 |  | 17.86% | 6 | 0 | 0 | 4 | 2 | 33.33%
BI/Data Mart Consolidated | BI Sprint 6 | 29 |  | 0 |  | 18 | 11 |  | 37.93% | 9 | 0 | 0 | 5 | 4 | 44.44%
BI/Data Mart Consolidated | BI Sprint 7 | 38 |  | 0 |  | 13 | 25 |  | 65.79% | 10 | 0 | 0 | 5 | 5 | 50%
BI/Data Mart Consolidated | BI Sprint 8 | 32 |  | 0 |  | 29 | 3 |  | 9.375% | 16 | 0 | 0 | 9 | 7 | 43.75%
BI/Data Mart Consolidated | BI-SHFB 2017 - Sprint 16 |  |  | 8 |  | 8 |  |  |  | 4 | 4 | 0 | 4 | 0 | 0%
BI/Data Mart Consolidated | BI-SHFB 2017 - Sprint 17 | 22 |  | 8 | 8 | 8 | 24 |  | 109.1% | 10 | 4 | 2 | 2 | 8 | 80%
BI/Data Mart Consolidated | BI-SHFB 2017 - Sprint 18 |  |  | 3 | 7 | 16 | 13 |  |  | 9 | 2 | 2 | 4 | 5 | 55.56%
BI/Data Mart Consolidated | BI-SHFB 2017 - Sprint 19 | 23 |  | 0 | 35 | 14 | 9 |  | 39.13% | 17 | 0 | 4 | 12 | 5 | 29.41%
BI/Data Mart Consolidated | BI-SHFB 2017 - Sprint 20 |  |  | 5 | 5 | 13 | 11 |  |  | 13 | 2 | 1 | 7 | 6 | 46.15%
BI/Data Mart Consolidated | BI-SHFB 2017 - Sprint 21 |  |  | 2 |  | 30 | 22 |  |  | 21 | 3 | 2 | 13 | 8 | 38.1%
BI/Data Mart Consolidated | BI-SHFB 2017 - Sprint 22 |  |  | 0 | 3 | 52 | 20 |  |  | 21 | 1 | 1 | 10 | 11 | 52.38%
BI/Data Mart Consolidated | BI-SHFB 2017 - Sprint 23 | 54 |  | 5 | 34 | 21 | 38 |  | 70.37% | 18 | 1 | 1 | 6 | 12 | 66.67%
BI/Data Mart Consolidated | BI-SHFB 2017 - Sprint 24 |  |  | 21 | 11 | 29 | 40 |  |  | 16 | 6 | 4 | 6 | 10 | 62.5%
BI/Data Mart Consolidated | BI-SHFB 2017 - Sprint 25 | 58 |  | 5 | 13 | 23 | 40 |  | 68.97% | 15 | 1 | 1 | 3 | 12 | 80%
BI/Data Mart Consolidated | BI-SHFB 2017 - Sprint 26 | 76 |  | 5 |  | 67 | 14 |  | 18.42% | 12 | 1 | 0 | 7 | 5 | 41.67%
BI/Data Mart Consolidated | BI-SHFB 2018 - Sprint 1 |  |  | 16 | 6 | 25 | 37 |  |  | 19 | 5 | 2 | 7 | 12 | 63.16%
BI/Data Mart Consolidated | BI-SHFB 2018 - Sprint 10 |  |  | 16 | 12 | 24 | 22 |  |  | 14 | 9 | 5 | 6 | 8 | 57.14%
BI/Data Mart Consolidated | BI-SHFB 2018 - Sprint 2 |  |  | 71 | 15 | 29 | 32 |  |  | 36 | 38 | 4 | 10 | 26 | 72.22%
BI/Data Mart Consolidated | BI-SHFB 2018 - Sprint 3 |  |  | 39 |  | 34 | 15 |  |  | 32 | 37 | 10 | 14 | 18 | 56.25%
BI/Data Mart Consolidated | BI-SHFB 2018 - Sprint 4 |  |  | 75 | 15 | 16 | 47 |  |  | 43 | 51 | 9 | 7 | 36 | 83.72%
BI/Data Mart Consolidated | BI-SHFB 2018 - Sprint 5 |  |  | 16 | 14 | 39 |  |  |  | 20 | 21 | 13 | 14 | 6 | 30%
BI/Data Mart Consolidated | BI-SHFB 2018 - Sprint 6 |  |  | 3 | 8 | 36 | 21 |  |  | 22 | 6 | 3 | 9 | 13 | 59.09%
BI/Data Mart Consolidated | BI-SHFB 2018 - Sprint 7 |  |  | 11 | 5 | 19 | 24 |  |  | 14 | 7 | 3 | 4 | 10 | 71.43%
BI/Data Mart Consolidated | BI-SHFB 2018 - Sprint 8 |  |  | 5 | 3 | 36 | 5 |  |  | 16 | 7 | 1 | 7 | 9 | 56.25%
BI/Data Mart Consolidated | BI-SHFB 2018 - Sprint 9 |  |  | 13 | 24 | 38 |  |  |  | 10 | 9 | 10 | 8 | 2 | 20%
BI/Data Mart Consolidated | RAPS-EDPS 2017 Sprint 12 |  |  | 0 |  |  | 1 |  |  | 3 | 0 | 0 | 0 | 3 | 100%
BI/Data Mart Consolidated | RAPS-EDPS Sprint 21 |  |  | 5 |  | 5 |  |  |  | 3 | 3 | 0 | 3 | 0 | 0%
BI/Data Mart Consolidated | RAPS-EDPS Sprint 22 |  |  | 0 |  | 3 |  |  |  | 3 | 0 | 0 | 3 | 0 | 0%
BI/Data Mart Consolidated | RAPS-EDPS Sprint 23 | 5 |  | 0 |  | 1 | 4 |  | 80% | 4 | 0 | 0 | 1 | 3 | 75%
BI/Data Mart Consolidated | Tableau Base Sprint 17 |  |  | 2 |  | 13 | 38.5 |  |  | 34 | 21 | 0 | 3 | 31 | 91.18%
BI/Data Mart Consolidated | Tableau-Base - Sprint 16 |  |  | 28.5 |  | 49.5 |  |  |  | 18 | 14 | 0 | 12 | 6 | 33.33%
BI/Data Mart P.D. Projects | 2018 Sprint 4 TrendyOutliers |  |  | 5 |  |  | 5 |  |  | 1 | 2 | 1 | 0 | 1 | 100%
BI/Data Mart P.D. Projects | 2018 Sprint 5 TrendyOutliers |  |  | 0 | [5 empty] | 1 | 1 | 0 | 0 | 1 | 100%
BI/Data Mart P.D. Projects | BI 2017 - Sprint 13 |  |  | 0 |  |  | 28 |  |  | 23 | 0 | 0 | 8 | 15 | 65.22%
BI/Data Mart P.D. Projects | BI 2017 - Sprint 14 |  |  | 3 | 3 | 8 | 32 |  |  | 26 | 4 | 1 | 8 | 18 | 69.23%
BI/Data Mart P.D. Projects | BI 2017 - Sprint 15 |  |  | 6.5 |  |  | 44.5 |  |  | 34 | 9 | 0 | 7 | 27 | 79.41%
BI/Data Mart P.D. Projects | BI 2017 - Sprint 16 |  |  | 4 |  | 3 | 38 |  |  | 25 | 3 | 0 | 7 | 18 | 72%
BI/Data Mart P.D. Projects | BI 2017 - Sprint 17 |  |  | 2 |  | 3 | 30 |  |  | 33 | 9 | 0 | 3 | 30 | 90.91%
BI/Data Mart P.D. Projects | BI Release 2 - Sprint 0 |  |  | 0 |  | 3 |  |  |  | 14 | 3 | 0 | 7 | 7 | 50%
BI/Data Mart P.D. Projects | BI Release 2 - Sprint 1 |  |  | 0 | 8 |  | 15 |  |  | 9 | 0 | 1 | 0 | 9 | 100%
BI/Data Mart P.D. Projects | BI Release 2 - Sprint 2 | 45 |  | 0 | 8 | 8 | 37 |  | 82.22% | 7 | 0 | 1 | 3 | 4 | 57.14%
BI/Data Mart P.D. Projects | BI Release 2 - Sprint 3 | 35 |  | 0 | 8 | 8 | 27 |  | 77.14% | 9 | 0 | 2 | 2 | 7 | 77.78%
BI/Data Mart P.D. Projects | BI Release 2 - Sprint 4 |  |  | 0 |  |  | 35 |  |  | 16 | 1 | 0 | 1 | 15 | 93.75%
BI/Data Mart P.D. Projects | BI Release 2 - Sprint 5 | 24 |  | 8 | 3 |  | 28 |  | 116.7% | 16 | 3 | 1 | 2 | 14 | 87.5%
BI/Data Mart P.D. Projects | BI Release 2 - Sprint 6 |  |  | 9 |  | 8 | 42 |  |  | 27 | 6 | 0 | 2 | 25 | 92.59%
BI/Data Mart P.D. Projects | BI Sprint 0 |  |  | 5 | 3 |  |  |  |  | 2 | 1 | 1 | 2 | 0 | 0%
BI/Data Mart P.D. Projects | BI Sprint 1 |  |  | 0 |  |  | 7 |  |  | 4 | 0 | 0 | 2 | 2 | 50%
BI/Data Mart P.D. Projects | BI Sprint 2 |  |  | 38 |  | 10 | 38 |  |  | 15 | 9 | 0 | 3 | 12 | 80%
BI/Data Mart P.D. Projects | BI Sprint 3 |  |  | 3 |  | 20 | 25 |  |  | 13 | 2 | 0 | 4 | 9 | 69.23%
BI/Data Mart P.D. Projects | BI Sprint 4 | 51 |  | 5 |  | 33 | 23 |  | 45.1% | 10 | 1 | 0 | 4 | 6 | 60%
BI/Data Mart P.D. Projects | BI Sprint 5 | 28 |  | 0 |  | 23 | 5 |  | 17.86% | 6 | 0 | 0 | 4 | 2 | 33.33%
BI/Data Mart P.D. Projects | BI Sprint 6 | 29 |  | 0 |  | 18 | 11 |  | 37.93% | 9 | 0 | 0 | 5 | 4 | 44.44%
BI/Data Mart P.D. Projects | BI Sprint 7 | 38 |  | 0 |  | 13 | 25 |  | 65.79% | 10 | 0 | 0 | 5 | 5 | 50%
BI/Data Mart P.D. Projects | BI Sprint 8 | 32 |  | 0 |  | 29 | 3 |  | 9.375% | 16 | 0 | 0 | 9 | 7 | 43.75%
BI/Data Mart P.D. Projects | BI-SHFB 2017 - Sprint 16 |  |  | 8 |  | 8 |  |  |  | 4 | 4 | 0 | 4 | 0 | 0%
BI/Data Mart P.D. Projects | BI-SHFB 2017 - Sprint 17 | 22 |  | 8 | 8 | 8 | 24 |  | 109.1% | 10 | 4 | 2 | 2 | 8 | 80%
BI/Data Mart P.D. Projects | BI-SHFB 2017 - Sprint 18 |  |  | 3 | 7 | 16 | 13 |  |  | 9 | 2 | 2 | 4 | 5 | 55.56%
BI/Data Mart P.D. Projects | BI-SHFB 2017 - Sprint 19 | 23 |  | 0 | 35 | 14 | 9 |  | 39.13% | 17 | 0 | 4 | 12 | 5 | 29.41%
BI/Data Mart P.D. Projects | BI-SHFB 2017 - Sprint 20 |  |  | 5 | 5 | 13 | 11 |  |  | 13 | 2 | 1 | 7 | 6 | 46.15%
BI/Data Mart P.D. Projects | BI-SHFB 2017 - Sprint 21 |  |  | 0 |  | 30 | 22 |  |  | 19 | 1 | 2 | 11 | 8 | 42.11%
BI/Data Mart P.D. Projects | BI-SHFB 2017 - Sprint 22 |  |  | 0 | 3 | 50 | 20 |  |  | 18 | 1 | 1 | 8 | 10 | 55.56%
BI/Data Mart P.D. Projects | BI-SHFB 2017 - Sprint 23 | 52 |  | 5 | 34 | 21 | 36 |  | 69.23% | 16 | 1 | 1 | 6 | 10 | 62.5%
BI/Data Mart P.D. Projects | BI-SHFB 2017 - Sprint 24 |  |  | 21 | 11 | 29 | 40 |  |  | 16 | 6 | 3 | 6 | 10 | 62.5%
BI/Data Mart P.D. Projects | BI-SHFB 2017 - Sprint 25 | 58 |  | 5 | 13 | 23 | 40 |  | 68.97% | 15 | 1 | 1 | 3 | 12 | 80%
BI/Data Mart P.D. Projects | BI-SHFB 2017 - Sprint 26 | 76 |  | 5 |  | 67 | 14 |  | 18.42% | 12 | 1 | 0 | 7 | 5 | 41.67%
BI/Data Mart P.D. Projects | BI-SHFB 2018 - Sprint 1 |  |  | 16 | 6 | 25 | 35 |  |  | 17 | 4 | 2 | 7 | 10 | 58.82%
BI/Data Mart P.D. Projects | BI-SHFB 2018 - Sprint 10 |  |  | 16 | 9 | 13 | 16 |  |  | 10 | 9 | 4 | 4 | 6 | 60%
BI/Data Mart P.D. Projects | BI-SHFB 2018 - Sprint 2 |  |  | 71 | 15 | 29 | 32 |  |  | 28 | 30 | 4 | 8 | 20 | 71.43%
BI/Data Mart P.D. Projects | BI-SHFB 2018 - Sprint 3 |  |  | 39 |  | 34 | 15 |  |  | 25 | 30 | 9 | 12 | 13 | 52%
BI/Data Mart P.D. Projects | BI-SHFB 2018 - Sprint 4 |  |  | 75 | 15 | 16 | 47 |  |  | 41 | 49 | 9 | 7 | 34 | 82.93%
BI/Data Mart P.D. Projects | BI-SHFB 2018 - Sprint 5 |  |  | 16 | 14 | 39 |  |  |  | 18 | 20 | 13 | 13 | 5 | 27.78%
BI/Data Mart P.D. Projects | BI-SHFB 2018 - Sprint 6 |  |  | 3 | 8 | 31 | 21 |  |  | 18 | 5 | 3 | 8 | 10 | 55.56%
BI/Data Mart P.D. Projects | BI-SHFB 2018 - Sprint 7 |  |  | 11 | 5 | 16 | 14 |  |  | 10 | 5 | 2 | 3 | 7 | 70%
BI/Data Mart P.D. Projects | BI-SHFB 2018 - Sprint 8 |  |  | 5 |  | 28 | 5 |  |  | 14 | 6 | 0 | 6 | 8 | 57.14%
BI/Data Mart P.D. Projects | BI-SHFB 2018 - Sprint 9 |  |  | 10 | 24 | 21 |  |  |  | 5 | 7 | 10 | 4 | 1 | 20%
BI/Data Mart P.D. Projects | RAPS-EDPS 2017 Sprint 12 |  |  | 0 |  |  | 1 |  |  | 3 | 0 | 0 | 0 | 3 | 100%
BI/Data Mart P.D. Projects | RAPS-EDPS Sprint 21 |  |  | 5 |  | 5 |  |  |  | 3 | 3 | 0 | 3 | 0 | 0%
BI/Data Mart P.D. Projects | RAPS-EDPS Sprint 22 |  |  | 0 |  | 3 |  |  |  | 3 | 0 | 0 | 3 | 0 | 0%
BI/Data Mart P.D. Projects | RAPS-EDPS Sprint 23 | 5 |  | 0 |  | 1 | 4 |  | 80% | 4 | 0 | 0 | 1 | 3 | 75%
BI/Data Mart P.D. Projects | Tableau Base Sprint 17 |  |  | 2 |  | 13 | 38.5 |  |  | 33 | 21 | 0 | 3 | 30 | 90.91%
BI/Data Mart P.D. Projects | Tableau-Base - Sprint 16 |  |  | 28.5 |  | 49.5 |  |  |  | 17 | 13 | 0 | 11 | 6 | 35.29%
BI/Data Mart Production Support | 2018 Sprint 10 Trendy Outliers |  |  | 1 | 6 |  | 1 |  |  | 1 | 1 | 2 | 0 | 1 | 100%
BI/Data Mart Production Support | 2018 Sprint 11 BI & Reporting |  |  | 7 | 11 |  | 11 |  |  | 8 | 6 | 3 | 2 | 6 | 75%
BI/Data Mart Production Support | 2018 Sprint 12 - Team 42 |  |  | 12 | 11 |  | 8 |  |  | 3 | 4 | 4 | 0 | 3 | 100%
BI/Data Mart Production Support | 2018 Sprint 13 - Team 42 | 0 |  | 7 | 14 | 3 | 1 |  |  | 2 | 3 | 4 | 1 | 1 | 50%
BI/Data Mart Production Support | 2018 Sprint 14 - Team 42 |  |  | 1 | 16 |  | 3 |  |  | 1 | 1 | 7 | 0 | 1 | 100%
BI/Data Mart Production Support | 2018 Sprint 15 - Team 42 |  |  | 5 | 30 | 4 |  |  |  | 2 | 2 | 11 | 2 | 0 | 0%
BI/Data Mart Production Support | 2018 Sprint 16 - Team 42 |  |  | 1 | 11 |  | 11 |  |  | 3 | 1 | 3 | 0 | 3 | 100%
BI/Data Mart Production Support | 2018 Sprint 17 - Team 42 |  |  | 2 | 12 |  | 11 |  |  | 4 | 1 | 3 | 0 | 4 | 100%
BI/Data Mart Production Support | 2018 Sprint 18 - Team 42 |  |  | 0 | 2 |  | 1 |  |  | 1 | 0 | 1 | 0 | 1 | 100%
BI/Data Mart Production Support | 2018 Sprint 19 - Team 42 |  |  | 0 | 5 |  |  |  |  | 0 | 0 | 2 | 0 | 0
BI/Data Mart Production Support | 2018 Sprint 20 - Team 42 |  |  | 0 | 12 |  | 5 |  |  | 1 | 0 | 3 | 0 | 1 | 100%
BI/Data Mart Production Support | 2018 Sprint 21 - Team 42 | 5 |  | 0 | 9 | 3 | 2 |  | 40% | 2 | 0 | 3 | 1 | 1 | 50%
BI/Data Mart Production Support | 2018 Sprint 22 - Team 42 |  |  | 0 | 16 |  |  |  |  | 0 | 0 | 6 | 0 | 0
BI/Data Mart Production Support | 2018 Sprint 23 - Team 42 |  |  | 3 | 11 |  |  |  |  | 0 | 1 | 4 | 0 | 0
BI/Data Mart Production Support | 2018 Sprint 24 - Team 42 |  |  | 0 | 8 |  | 8 |  |  | 1 | 0 | 5 | 0 | 1 | 100%
BI/Data Mart Production Support | 2018 Sprint 25 - Team 42 | 6 |  | 0 | 10 | 1 | 5 |  | 83.33% | 2 | 0 | 5 | 1 | 1 | 50%
BI/Data Mart Production Support | 2018 Sprint 26 - Team 42 |  |  | 0 | 3 |  |  |  |  | 1 | 1 | 2 | 1 | 0 | 0%
BI/Data Mart Production Support | 2018 Sprint 3 TrendyOutliers |  |  | 19 |  | 5 | 9 |  |  | 7 | 7 | 0 | 3 | 4 | 57.14%
BI/Data Mart Production Support | 2018 Sprint 4 TrendyOutliers | 5 |  | 15 |  | 5 | 15 |  | 300% | 4 | 3 | 0 | 1 | 3 | 75%
BI/Data Mart Production Support | 2018 Sprint 5 TrendyOutliers |  |  | 2 | 7 | 10 | 3 |  |  | 4 | 2 | 6 | 3 | 1 | 25%
BI/Data Mart Production Support | 2018 Sprint 6 TrendyOutliers |  |  | 0 | 9 | 3 | 10 |  |  | 5 | 0 | 3 | 2 | 3 | 60%
BI/Data Mart Production Support | 2018 Sprint 7 Trendy Outliers |  |  | 0 | 12 | 3 |  |  |  | 1 | 0 | 4 | 1 | 0 | 0%
BI/Data Mart Production Support | 2018 Sprint 8 Trendy Outliers |  |  | 0 | 12 |  | 5 |  |  | 1 | 0 | 4 | 0 | 1 | 100%
BI/Data Mart Production Support | 2018 Sprint 9 Trendy Outliers |  |  | 0 | 5 |  | 1 |  |  | 1 | 0 | 2 | 0 | 1 | 100%
BI/Data Mart Production Support | 2019 Sprint 01 - Team 42 |  |  | 1 | 6 | 1 |  |  |  | 3 | 3 | 3 | 2 | 1 | 33.33%
BI/Data Mart Production Support | 2019 Sprint 02 - Team 42 |  |  | 0 | 7 | 5 |  |  |  | 1 | 0 | 4 | 1 | 0 | 0%
BI/Data Mart Production Support | 2019 Sprint 03 - Team 42 | 10 |  | 0 | 7 | 5 | 6 |  | 60% | 3 | 0 | 3 | 1 | 2 | 66.67%
BI/Data Mart Production Support | 2019 Sprint 04 - Team 42 |  |  | 0 | 1 | 2 |  |  |  | 1 | 0 | 1 | 1 | 0 | 0%
BI/Data Mart Production Support | 2019 Sprint 05 - Team 42 |  |  | 1 | 3 |  | 1 |  |  | 1 | 1 | 1 | 0 | 1 | 100%
BI/Data Mart Production Support | 2019 Sprint 06- Team 42 |  |  | 0 | 12 |  |  |  |  | 0 | 0 | 4 | 0 | 0
BI/Data Mart Production Support | 2019 Sprint 07 - Team 42 |  |  | 3 | 9 |  | 4 |  |  | 2 | 1 | 4 | 0 | 2 | 100%
BI/Data Mart Production Support | 2019 Sprint 08 - Team 42 |  |  | 0 | 14 |  | 3 |  |  | 1 | 0 | 8 | 0 | 1 | 100%
BI/Data Mart Production Support | 2019 Sprint 09 - Team 42 |  |  | 0 | 5 |  | 5 |  |  | 1 | 0 | 4 | 0 | 1 | 100%
BI/Data Mart Production Support | 2019 Sprint 10 - Team 42 | 7 |  | 0 | 13 | 5 | 2 |  | 28.57% | 3 | 0 | 4 | 1 | 2 | 66.67%
BI/Data Mart Production Support | 2019 Sprint 11 - Team 42 |  |  | 0 | 3 |  | 6 |  |  | 2 | 0 | 2 | 0 | 2 | 100%
BI/Data Mart Production Support | 2019 Sprint 12 - Team 42 |  |  | 1 | 9 |  |  |  |  | 0 | 1 | 6 | 0 | 0
BI/Data Mart Production Support | 2019 Sprint 13 - Team 42 |  |  | 2 | 4 |  |  |  |  | 0 | 1 | 2 | 0 | 0
BI/Data Mart Production Support | 2019 Sprint 14 - Team 42 |  |  | 0 | 2 |  | 5 |  |  | 2 | 0 | 1 | 0 | 2 | 100%
BI/Data Mart Production Support | 2019 Sprint 15 - Team 42 |  |  | 0 | 11 |  |  |  |  | 0 | 0 | 5 | 0 | 0
BI/Data Mart Production Support | 2019 Sprint 16 - Team 42 |  |  | 0 | 10 |  |  |  |  | 0 | 0 | 3 | 0 | 0
BI/Data Mart Production Support | 2019 Sprint 17 - Team 42 |  |  | 0 | 12 |  |  |  |  | 1 | 0 | 6 | 0 | 1 | 100%
BI/Data Mart Production Support | BI 2017 - Sprint 16 |  |  | 0 | [5 empty] | 1 | 0 | 0 | 1 | 0 | 0%
BI/Data Mart Production Support | BI 2017 - Sprint 17 |  |  | 0 | [5 empty] | 1 | 0 | 0 | 1 | 0 | 0%
BI/Data Mart Production Support | BI-SHFB 2018 - Sprint 10 |  |  | 0 |  |  | 3 |  |  | 1 | 0 | 0 | 0 | 1 | 100%
BI/Data Mart Production Support | BI-SHFB 2018 - Sprint 5 |  |  | 0 | [5 empty] | 1 | 1 | 0 | 0 | 1 | 100%
BI/Data Mart Production Support | BI-SHFB 2018 - Sprint 6 |  |  | 0 | [5 empty] | 2 | 0 | 0 | 0 | 2 | 100%
BI/Data Mart Production Support | BI-SHFB 2018 - Sprint 7 |  |  | 0 |  |  | 5 |  |  | 2 | 1 | 0 | 0 | 2 | 100%
BI/Data Mart Production Support | BI-SHFB 2018 - Sprint 9 |  |  | 3 |  | 3 |  |  |  | 1 | 1 | 0 | 1 | 0 | 0%
BI/Data Mart Production Support | Tableau Base Sprint 17 |  |  | 0 | [5 empty] | 1 | 0 | 0 | 0 | 1 | 100%
BI/Data Mart Production Support | Tableau-Base - Sprint 16 |  |  | 0 | [5 empty] | 1 | 1 | 0 | 1 | 0 | 0%
Commercial Backlog | 2019 Sprint 5 |  | 8 | 0 |  | 8 |  | 0 |  | 1 | 0 | 0 | 1 | 0 | 0%
Commercial Backlog | 2021 Black Box Ready |  |  | 0 | [5 empty] | 1 | 0 | 0 | 1 | 0 | 0%
Commercial Backlog | 2021 Blackbox Sprint 6 |  | 3 | 0 |  | 3 |  | 0 |  | 1 | 0 | 0 | 1 | 0 | 0%
Commercial Backlog | 2021 Blackbox Sprint 7 |  |  | 0 |  | 11 |  |  |  | 2 | 0 | 0 | 2 | 0 | 0%
Commercial Backlog | 2021 Blackbox Sprint 8 |  |  | 0 |  | 3 |  |  |  | 1 | 0 | 0 | 1 | 0 | 0%
Commercial Backlog | 2021 Chargers Sprint 7 |  |  | 0 |  | 8 |  |  |  | 1 | 0 | 0 | 1 | 0 | 0%
Commercial Board | 2018 BP Sprint 12 |  |  | 0 |  | 3 |  |  |  | 1 | 0 | 0 | 1 | 0 | 0%
Commercial Board | 2018 BP Sprint 13 |  |  | 0 |  |  | 3 |  |  | 1 | 0 | 0 | 0 | 1 | 100%
Commercial Board | 2018 Comm Sprint 18 | 83 |  | 0 |  | 15 | 68 |  | 81.93% | 17 | 0 | 0 | 3 | 14 | 82.35%
Commercial Board | 2018 Comm Sprint 19 |  |  | 15 | 3 | 18 | 102 |  |  | 30 | 5 | 1 | 3 | 27 | 90%
Commercial Board | 2018 Comm Sprint 20 |  |  | 5 | 2 | 5 | 109 |  |  | 26 | 1 | 2 | 1 | 25 | 96.15%
Commercial Board | 2018 Comm Sprint 21 |  |  | 5 |  | 33 | 125 |  |  | 32 | 2 | 0 | 5 | 27 | 84.38%
Commercial Board | 2018 Comm Sprint 22 |  |  | 8 | 15 | 15 | 151 |  |  | 33 | 4 | 3 | 3 | 30 | 90.91%
Commercial Board | 2018 Comm Sprint 23 |  |  | 5 | 5 | 57 | 168 |  |  | 46 | 10 | 1 | 16 | 30 | 65.22%
Commercial Board | 2018 Comm Sprint 24 |  |  | 167 | 5 | 61 | 191 |  |  | 61 | 47 | 1 | 14 | 47 | 77.05%
Commercial Board | 2018 Comm Sprint 25 |  |  | 62 |  | 6 | 56 |  |  | 19 | 19 | 0 | 2 | 17 | 89.47%
Commercial Board | 2018 Comm Sprint 26 | 35 |  | 0 | 10 | 32 | 3 |  | 8.571% | 15 | 0 | 2 | 14 | 1 | 6.667%
Commercial Board | 2019 Comm Sprint 1 |  |  | 37 | 3 |  | 144 |  |  | 47 | 13 | 1 | 0 | 47 | 100%
Commercial Board | 2019 Comm Sprint 10 |  |  | 18 |  | 13 | 98 |  |  | 28 | 5 | 0 | 2 | 26 | 92.86%
Commercial Board | 2019 Comm Sprint 11 |  |  | 13 |  |  | 105 |  |  | 25 | 4 | 0 | 0 | 25 | 100%
Commercial Board | 2019 Comm Sprint 12 | 86 |  | 0 |  | 5 | 81 |  | 94.19% | 17 | 0 | 0 | 1 | 16 | 94.12%
Commercial Board | 2019 Comm Sprint 13 |  |  | 3 |  | 5 | 86 |  |  | 24 | 3 | 0 | 1 | 23 | 95.83%
Commercial Board | 2019 Comm Sprint 14 | 71 |  | 21 |  | 8 | 84 |  | 118.3% | 22 | 5 | 0 | 1 | 21 | 95.45%
Commercial Board | 2019 Comm Sprint 15 |  |  | 13 |  | 5 | 94 |  |  | 25 | 8 | 0 | 1 | 24 | 96%
Commercial Board | 2019 Comm Sprint 16 |  |  | 9 | 5 | 5 | 126 |  |  | 28 | 4 | 2 | 1 | 27 | 96.43%
Commercial Board | 2019 Comm Sprint 17 |  |  | 0 |  | 32 | 60 |  |  | 35 | 6 | 0 | 11 | 24 | 68.57%
Commercial Board | 2019 Comm Sprint 18 |  |  | 46 | 5 | 38 | 94 |  |  | 40 | 20 | 3 | 12 | 28 | 70%
Commercial Board | 2019 Comm Sprint 19 |  |  | 0 |  | 37 | 73 |  |  | 34 | 7 | 0 | 11 | 23 | 67.65%
Commercial Board | 2019 Comm Sprint 2 |  |  | 0 | 9 |  | 76 |  |  | 22 | 0 | 3 | 0 | 22 | 100%
Commercial Board | 2019 Comm Sprint 20 |  | 132 | 8 |  | 23 | 117 | 117 |  | 36 | 6 | 0 | 7 | 29 | 80.56%
Commercial Board | 2019 Comm Sprint 21 | 102 | 110 | 13 | 5 | 53 | 65 | 65 | 63.73% | 29 | 2 | 1 | 12 | 17 | 58.62%
Commercial Board | 2019 Comm Sprint 22 | 143 | 143 | 8 |  | 8 | 137 | 137 | 95.8% | 36 | 3 | 0 | 1 | 35 | 97.22%
Commercial Board | 2019 Comm Sprint 23 |  | 88 | 3 |  | 3 | 85 | 85 |  | 17 | 1 | 0 | 1 | 16 | 94.12%
Commercial Board | 2019 Comm Sprint 24 |  | 43 | 7 |  | 8 | 42 | 42 |  | 14 | 3 | 0 | 2 | 12 | 85.71%
Commercial Board | 2019 Comm Sprint 25 |  | 62 | 21 | 13 | 5 | 65 | 65 |  | 19 | 5 | 2 | 1 | 18 | 94.74%
Commercial Board | 2019 Comm Sprint 26 |  | 35 | 5 |  |  | 40 | 40 |  | 10 | 1 | 0 | 0 | 10 | 100%
Commercial Board | 2019 Comm Sprint 3 |  |  | 14 |  | 5 | 119 |  |  | 28 | 6 | 0 | 1 | 27 | 96.43%
Commercial Board | 2019 Comm Sprint 4 |  |  | 18 | 15 | 29 | 93 |  |  | 28 | 5 | 3 | 6 | 22 | 78.57%
Commercial Board | 2019 Comm Sprint 5 |  |  | 23 |  | 21 | 98 |  |  | 26 | 7 | 0 | 4 | 22 | 84.62%
Commercial Board | 2019 Comm Sprint 6 |  |  | 0 |  | 41 | 73 |  |  | 26 | 4 | 0 | 6 | 20 | 76.92%
Commercial Board | 2019 Comm Sprint 7 |  |  | 0 |  | 3 | 99 |  |  | 23 | 1 | 0 | 1 | 22 | 95.65%
Commercial Board | 2019 Comm Sprint 8 |  |  | 8 |  | 5 | 92 |  |  | 15 | 3 | 0 | 1 | 14 | 93.33%
Commercial Board | 2019 Comm Sprint 9 |  |  | 3 |  | 8 | 72 |  |  | 20 | 4 | 0 | 1 | 19 | 95%
Commercial Board | Team Raider Sprint 14 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Commercial Board | Tech Enablement QME Backlog |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Copy of Team Dynamo Sprint Board | 2017 BP Sprint 12 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Copy of Team Dynamo Sprint Board | 2017 BP Sprint 13 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Copy of Team Dynamo Sprint Board | 2017 BP Sprint 14 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Copy of Team Dynamo Sprint Board | 2017 BP Sprint 16 |  |  | 0 |  |  | 5 |  |  | 1 | 0 | 0 | 0 | 1 | 100%
Copy of Team Dynamo Sprint Board | 2017 BP Sprint 17 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Copy of Team Dynamo Sprint Board | 2017 BP Sprint 19 |  |  | 0 |  |  | 5 |  |  | 1 | 0 | 0 | 0 | 1 | 100%
Copy of Team Dynamo Sprint Board | 2017 BP Sprint 21 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Copy of Team Dynamo Sprint Board | 2017 BP Sprint 22 |  |  | 0 |  |  | 3 |  |  | 1 | 0 | 0 | 0 | 1 | 100%
Copy of Team Dynamo Sprint Board | 2017 BP Sprint 23 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Copy of Team Dynamo Sprint Board | 2017 BP Sprint 24 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Copy of Team Dynamo Sprint Board | 2017 BP Sprint 25 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Copy of Team Dynamo Sprint Board | 2017 BP Sprint 26 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Copy of Team Dynamo Sprint Board | 2018 BP Sprint 1 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Copy of Team Dynamo Sprint Board | 2018 BP Sprint 18 |  |  | 0 |  |  | 8 |  |  | 1 | 0 | 0 | 0 | 1 | 100%
Copy of Team Dynamo Sprint Board | 2018 BP Sprint 21 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Copy of Team Dynamo Sprint Board | 2018 BP Sprint 22 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Copy of Team Dynamo Sprint Board | 2018 BP Sprint 23 |  |  | 0 |  |  | 5 |  |  | 1 | 0 | 0 | 0 | 1 | 100%
Copy of Team Dynamo Sprint Board | 2018 BP Sprint 25 | 5 |  | 2 |  | 5 | 2 |  | 40% | 2 | 1 | 0 | 1 | 1 | 50%
Copy of Team Dynamo Sprint Board | 2018 BP Sprint 26 |  |  | 0 |  | 5 |  |  |  | 1 | 0 | 0 | 1 | 0 | 0%
Copy of Team Dynamo Sprint Board | 2018 BP Sprint 6 | 11 |  | 0 |  | 3 | 8 |  | 72.73% | 2 | 0 | 0 | 1 | 1 | 50%
Copy of Team Dynamo Sprint Board | 2018 BP Sprint 7 |  |  | 0 |  |  | 3 |  |  | 1 | 0 | 0 | 0 | 1 | 100%
Copy of Team Dynamo Sprint Board | 2019 BP Sprint 12 |  |  | 0 |  |  | 21 |  |  | 3 | 0 | 0 | 0 | 3 | 100%
Copy of Team Dynamo Sprint Board | 2019 BP Sprint 14 |  |  | 0 |  |  | 8 |  |  | 1 | 0 | 0 | 0 | 1 | 100%
Copy of Team Dynamo Sprint Board | 2019 BP Sprint 15 |  |  | 10 |  |  | 10 |  |  | 2 | 2 | 0 | 0 | 2 | 100%
Copy of Team Dynamo Sprint Board | 2019 BP Sprint 25 |  | 0 | 0 |  |  |  | 0 |  | 0 | 1 | 1 | 0 | 0
Copy of Team Dynamo Sprint Board | 2019 BP Sprint 5 |  |  | 0 |  |  | 5 |  |  | 1 | 0 | 0 | 0 | 1 | 100%
Copy of Team Dynamo Sprint Board | Base Platform Sprint 39 |  |  | 0 |  | 10 |  |  |  | 1 | 0 | 0 | 1 | 0 | 0%
Copy of Team Dynamo Sprint Board | Base Platform Sprint 43 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Copy of Team Dynamo Sprint Board | Sprint 1 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Data Management Development | Base Platform Sprint 37 |  | 0 | 0 | 3 |  |  | 0 |  | 1 | 0 | 8 | 0 | 1 | 100%
Data Management Development | Base Platform Sprint 39 |  | 0 | 0 |  |  |  | 0 |  | 1 | 1 | 7 | 1 | 0 | 0%
Data Management Development | Base Platform Sprint 40 |  | 5 | 13 |  |  | 13 | 13 |  | 8 | 8 | 0 | 0 | 8 | 100%
Data Management Development | Base Platform Sprint 41 |  | 6 | 0 |  |  |  | 0 |  | 0 | 0 | 1 | 0 | 0
Data Management Development | Base Platform Sprint 42 |  | 5 | 0 |  |  |  | 0 |  | 0 | 0 | 1 | 0 | 0
Data Management Development | Base Platform Sprint 43 |  | 7 | 3 | 2 |  | 3 | 3 |  | 1 | 1 | 3 | 0 | 1 | 100%
Data Management Development | Sprint 1 |  |  | 0 | 8 |  | 16 |  |  | 2 | 0 | 1 | 0 | 2 | 100%
Data Management Development | Sprint 2 |  |  | 0 |  | 8 |  |  |  | 4 | 0 | 0 | 2 | 2 | 50%
Data Management Development | Sprint 27 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Data Management Development | Sprint 28 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Data Management Development | Sprint 3 | 31 |  | 5 |  | 10 | 26 |  | 83.87% | 5 | 1 | 0 | 2 | 3 | 60%
Data Management Development | Sprint 32 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Data Management Development | Sprint 34 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Data Management Development | Sprint 4 | 10 |  | 0 |  | 5 | 5 |  | 50% | 3 | 0 | 0 | 1 | 2 | 66.67%
Data Management Development | Sprint 5 |  |  | 0 | [5 empty] | 2 | 3 | 1 | 0 | 2 | 100%
Data Management Development | Team Raider Sprint 14 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | 2017 BP Sprint 12 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | 2017 BP Sprint 13 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | 2017 BP Sprint 14 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | 2017 BP Sprint 16 |  |  | 0 |  |  | 5 |  |  | 1 | 0 | 0 | 0 | 1 | 100%
ETP Backlog | 2017 BP Sprint 17 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | 2017 BP Sprint 19 |  |  | 0 |  |  | 5 |  |  | 1 | 0 | 0 | 0 | 1 | 100%
ETP Backlog | 2017 BP Sprint 21 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | 2017 BP Sprint 22 |  |  | 0 |  |  | 3 |  |  | 1 | 0 | 0 | 0 | 1 | 100%
ETP Backlog | Base Platform Sprint 39 |  |  | 0 |  | 10 |  |  |  | 1 | 0 | 0 | 1 | 0 | 0%
ETP Backlog | Base Platform Sprint 43 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | PK Sprint 10 |  |  | 0 | [5 empty] | 0 | 1 | 1 | 0 | 0
ETP Backlog | PK Sprint 11 |  |  | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
ETP Backlog | PK Sprint 12 |  |  | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
ETP Backlog | PK Sprint 13 |  |  | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
ETP Backlog | PK Sprint 6 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | PK Sprint 7 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | PK Sprint 8 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | PK Sprint 9 |  |  | 0 | [5 empty] | 0 | 1 | 1 | 0 | 0
ETP Backlog | Retrieval Kanban |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 1 |  |  | 0 | [5 empty] | 1 | 0 | 0 | 1 | 0 | 0%
ETP Backlog | Sprint 10 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 11 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 12 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 13 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 14 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 15 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 16 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 17 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 18 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 19 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 2 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 20 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 21 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 22 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 23 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 24 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 25 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 26 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 27 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 28 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 29 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 3 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 30 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 31 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 4 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 5 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 6 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 7 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 8 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
ETP Backlog | Sprint 9 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Jira Sandbox - Consolidated Scrum Board | Test Sprint Team 1 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Jira Sandbox - Consolidated Scrum Board | Test Sprint X Team 1 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Jira Sandbox - Consolidated Scrum Board | Test Sprint X Team 2 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Jira Sandbox - Project Scrum Board | Sprint 4 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Jira Sandbox - Project Scrum Board | Sprint 5 |  | 20 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
Jira Sandbox - Project Scrum Board | Test Sprint 1 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Jira Sandbox - Project Scrum Board | Test Sprint Team 1 |  | 40 | 22 |  | 40 | 22 | 22 |  | 5 | 3 | 0 | 3 | 2 | 40%
Jira Sandbox - Project Scrum Board | Test Sprint X Team 1 |  |  | 0 | [5 empty] | 1 | 0 | 0 | 1 | 0 | 0%
Jira Sandbox - Project Scrum Board | Test Sprint X Team 2 |  |  | 0 | [5 empty] | 1 | 0 | 0 | 1 | 0 | 0%
JIRA Sandbox - Small Enhancements Scrum Board | 2017 Sprint 12 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
JIRA Sandbox - Small Enhancements Scrum Board | 2017 Sprint 13 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
MRR Consolidated | Base Platform Sprint 37 |  |  | 0 | [5 empty] | 1 | 1 | 0 | 0 | 1 | 100%
MRR Consolidated | Base Platform Sprint 40 |  |  | 0 | [5 empty] | 1 | 1 | 0 | 0 | 1 | 100%
MRR Consolidated | MRR- Sprint 35 |  |  | 2 |  |  | 57.5 |  |  | 31 | 2 | 0 | 3 | 28 | 90.32%
MRR Consolidated | MRR- Sprint 36 |  |  | 3.5 | 10 | 3.5 | 25.5 |  |  | 20 | 8 | 6 | 7 | 13 | 65%
MRR Consolidated | MRR- Sprint 37 |  |  | 8 | 3 |  | 53.5 |  |  | 56 | 41 | 1 | 0 | 56 | 100%
MRR Consolidated | MRR- Sprint 38 |  |  | 18 | 13 | 33 | 46.5 |  |  | 49 | 17 | 10 | 12 | 37 | 75.51%
MRR Consolidated | MRR- Sprint 39 |  |  | 33.5 |  | 25.5 | 61.5 |  |  | 50 | 20 | 1 | 10 | 40 | 80%
MRR Consolidated | MRR- Sprint 40 |  |  | 47.5 | 7.5 | 26 | 70.5 |  |  | 37 | 22 | 5 | 8 | 29 | 78.38%
MRR Consolidated | MRR- Sprint 41 |  |  | 48 | 2 | 11.5 | 80.5 |  |  | 47 | 20 | 3 | 6 | 41 | 87.23%
MRR Consolidated | MRR- Sprint 42 |  |  | 11.5 | 5 | 10 | 77.5 |  |  | 52 | 18 | 9 | 6 | 46 | 88.46%
MRR Consolidated | MRR- Sprint 43 |  |  | 9 | 5 |  | 96.5 |  |  | 55 | 16 | 2 | 0 | 55 | 100%
MRR Consolidated | MRR- Sprint 44 |  |  | 6 |  | 21 | 57 |  |  | 51 | 19 | 0 | 8 | 43 | 84.31%
MRR Consolidated | MRR- Sprint 45 |  |  | 23 | 10 |  | 99 |  |  | 45 | 19 | 6 | 3 | 42 | 93.33%
MRR Consolidated | MRR- Sprint 46 |  |  | 30 | 6 | 18 | 74 |  |  | 51 | 19 | 17 | 8 | 43 | 84.31%
MRR Consolidated | MRR- Sprint 47 |  |  | 31 | 4 | 8 | 83.5 |  |  | 68 | 43 | 6 | 9 | 59 | 86.76%
MRR Consolidated | PK Sprint 6 |  |  | 0 | [5 empty] | 1 | 8 | 2 | 0 | 1 | 100%
MRR Consolidated | PK Sprint 8 |  |  | 0 | [5 empty] | 1 | 2 | 1 | 0 | 1 | 100%
MRR Consolidated | Retrieval Kanban |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
MRR Consolidated | Sprint 10 |  |  | 0 | [5 empty] | 10 | 7 | 20 | 0 | 10 | 100%
MRR Consolidated | Sprint 11 |  |  | 0 | [5 empty] | 3 | 17 | 27 | 0 | 3 | 100%
MRR Consolidated | Sprint 12 |  |  | 0 | [5 empty] | 29 | 27 | 22 | 0 | 29 | 100%
MRR Consolidated | Sprint 13 |  |  | 0 | [5 empty] | 49 | 26 | 24 | 0 | 49 | 100%
MRR Consolidated | Sprint 14 |  |  | 0 | [5 empty] | 40 | 20 | 14 | 0 | 40 | 100%
MRR Consolidated | Sprint 15 |  |  | 8 | [5 empty] | 29 | 34 | 15 | 0 | 29 | 100%
MRR Consolidated | Sprint 16 |  |  | 8 | [5 empty] | 12 | 10 | 8 | 0 | 12 | 100%
MRR Consolidated | Sprint 17 |  |  | 0 | [5 empty] | 38 | 9 | 3 | 0 | 38 | 100%
MRR Consolidated | Sprint 18 |  |  | 0 | [5 empty] | 14 | 10 | 10 | 0 | 14 | 100%
MRR Consolidated | Sprint 19 |  |  | 0 | [5 empty] | 10 | 22 | 11 | 0 | 10 | 100%
MRR Consolidated | Sprint 2 |  |  | 0 |  |  | 21 |  |  | 2 | 0 | 2 | 0 | 2 | 100%
MRR Consolidated | Sprint 20 |  |  | 0 | [5 empty] | 13 | 6 | 17 | 0 | 13 | 100%
MRR Consolidated | Sprint 21 |  |  | 0 | [5 empty] | 17 | 13 | 10 | 0 | 17 | 100%
MRR Consolidated | Sprint 22 |  |  | 0 | [5 empty] | 36 | 38 | 7 | 0 | 36 | 100%
MRR Consolidated | Sprint 23 |  |  | 0 | [5 empty] | 33 | 22 | 9 | 0 | 33 | 100%
MRR Consolidated | Sprint 24 |  |  | 0 | [5 empty] | 19 | 18 | 17 | 0 | 19 | 100%
MRR Consolidated | Sprint 25 |  |  | 0 | 3 |  |  |  |  | 19 | 7 | 25 | 0 | 19 | 100%
MRR Consolidated | Sprint 26 |  |  | 0 | 10 |  |  |  |  | 0 | 5 | 27 | 0 | 0
MRR Consolidated | Sprint 27 |  |  | 0 | 8 |  | 1 |  |  | 1 | 1 | 12 | 0 | 1 | 100%
MRR Consolidated | Sprint 28 |  |  | 1 | 6 |  | 4 |  |  | 12 | 8 | 6 | 0 | 12 | 100%
MRR Consolidated | Sprint 29 |  |  | 3 |  | 29 | 3 |  |  | 14 | 3 | 1 | 11 | 3 | 21.43%
MRR Consolidated | Sprint 3 |  |  | 0 |  |  | 23 |  |  | 4 | 0 | 1 | 0 | 4 | 100%
MRR Consolidated | Sprint 30 |  |  | 31 | 3 | 9 | 28.5 |  |  | 18 | 12 | 2 | 4 | 14 | 77.78%
MRR Consolidated | Sprint 31 |  |  | 33.5 |  | 6 | 27.5 |  |  | 19 | 22 | 1 | 5 | 14 | 73.68%
MRR Consolidated | Sprint 32 |  |  | 0.5 | 8 | 3 | 20.5 |  |  | 14 | 1 | 1 | 1 | 13 | 92.86%
MRR Consolidated | Sprint 33 |  |  | 13 |  | 16 | 8 |  |  | 24 | 14 | 0 | 5 | 19 | 79.17%
MRR Consolidated | Sprint 34 |  |  | 13.5 | 3 | 11.5 | 22 |  |  | 28 | 9 | 1 | 11 | 17 | 60.71%
MRR Consolidated | Sprint 4 |  |  | 0 | [5 empty] | 9 | 3 | 5 | 0 | 9 | 100%
MRR Consolidated | Sprint 6 |  |  | 0 | [5 empty] | 7 | 11 | 13 | 0 | 7 | 100%
MRR Consolidated | Sprint 7 |  |  | 0 | [5 empty] | 10 | 15 | 6 | 0 | 10 | 100%
MRR Consolidated | Sprint 8 |  |  | 0 | [5 empty] | 9 | 10 | 5 | 0 | 9 | 100%
MRR Consolidated | Sprint 9 |  |  | 0 | [5 empty] | 12 | 20 | 14 | 0 | 12 | 100%
MRR P.D. Projects | 2017 Sprint 12 |  |  | 5 | 21 |  | 38.5 |  |  | 13 | 4 | 4 | 0 | 13 | 100%
MRR P.D. Projects | 2017 Sprint 13 | 66 |  | 0 | 4 | 39 | 32 |  | 48.48% | 16 | 0 | 3 | 7 | 9 | 56.25%
MRR P.D. Projects | 2017 Sprint 14 |  |  | 41 | 7 | 74 | 20 |  |  | 22 | 11 | 2 | 13 | 9 | 40.91%
MRR P.D. Projects | 2017 Sprint 15 |  |  | 74 |  |  | 128 |  |  | 27 | 15 | 0 | 0 | 27 | 100%
MRR P.D. Projects | 2017 Sprint 16 |  |  | 0 | 3 | 14 | 67 |  |  | 26 | 7 | 4 | 4 | 22 | 84.62%
MRR P.D. Projects | 2017 Sprint 17 |  |  | 25 | 24 | 6 | 78 |  |  | 42 | 24 | 7 | 3 | 39 | 92.86%
MRR P.D. Projects | 2017 Sprint 18 |  |  | 12 | 11 | 8 | 31 |  |  | 45 | 39 | 9 | 3 | 42 | 93.33%
MRR P.D. Projects | 2017 Sprint 19 |  |  | 16 | 3 | 5 | 49 |  |  | 55 | 40 | 3 | 1 | 54 | 98.18%
MRR P.D. Projects | 2017 Sprint 20 |  |  | 5 |  | 13 | 31 |  |  | 23 | 14 | 3 | 7 | 16 | 69.57%
MRR P.D. Projects | 2017 Sprint 21 |  |  | 13 | 8 | 21 | 24 |  |  | 26 | 18 | 1 | 4 | 22 | 84.62%
MRR P.D. Projects | 2017 Sprint 22 |  |  | 29 | 8 | 26 | 23 |  |  | 18 | 14 | 3 | 4 | 14 | 77.78%
MRR P.D. Projects | 2017 Sprint 23 |  |  | 26 |  | 32 | 28 |  |  | 19 | 11 | 1 | 4 | 15 | 78.95%
MRR P.D. Projects | 2017 Sprint 24 |  |  | 81 | 31 | 11 | 44 |  |  | 29 | 40 | 11 | 5 | 24 | 82.76%
MRR P.D. Projects | 2017 Sprint 25 |  |  | 16 | 6 | 10 | 21 |  |  | 17 | 15 | 3 | 2 | 15 | 88.24%
MRR P.D. Projects | 2017 Sprint 26 |  |  | 10 | 8 |  | 26 |  |  | 4 | 4 | 4 | 0 | 4 | 100%
MRR P.D. Projects | 2017 Star Sprint 19 | 53 |  | 0 |  | 6 | 47 |  | 88.68% | 15 | 0 | 0 | 2 | 13 | 86.67%
MRR P.D. Projects | 2017 Star Sprint 20 |  |  | 8 |  |  | 27 |  |  | 10 | 5 | 0 | 1 | 9 | 90%
MRR P.D. Projects | 2017 Star Sprint 21 |  |  | 0 |  |  | 13 |  |  | 7 | 5 | 0 | 0 | 7 | 100%
MRR P.D. Projects | 2017 Star Sprint 22 |  |  | 0 | 8 | 8 | 15 |  |  | 8 | 4 | 1 | 1 | 7 | 87.5%
MRR P.D. Projects | 2017 Star Sprint 23 |  |  | 8 |  |  | 14 |  |  | 4 | 1 | 0 | 0 | 4 | 100%
MRR P.D. Projects | 2017 Star Sprint 24 |  |  | 5 | 10 | 5 | 16 |  |  | 12 | 9 | 5 | 4 | 8 | 66.67%
MRR P.D. Projects | 2017 Star Sprint 25 |  |  | 10 |  | 2 | 26 |  |  | 15 | 8 | 0 | 2 | 13 | 86.67%
MRR P.D. Projects | 2017 Star Sprint 26 |  |  | 0 | [5 empty] | 4 | 4 | 0 | 0 | 4 | 100%
MRR P.D. Projects | 2018 Sprint 1 |  |  | 2 | 8 |  | 18 |  |  | 14 | 8 | 5 | 0 | 14 | 100%
MRR P.D. Projects | 2018 Sprint 10 |  |  | 51 | 30 | 5 | 8 |  |  | 5 | 13 | 8 | 3 | 2 | 40%
MRR P.D. Projects | 2018 Sprint 11 |  |  | 23 | 7 | 16 |  |  |  | 5 | 14 | 9 | 4 | 1 | 20%
MRR P.D. Projects | 2018 Sprint 12 |  |  | 29 | 7 | 22 |  |  |  | 6 | 12 | 6 | 6 | 0 | 0%
MRR P.D. Projects | 2018 Sprint 13 |  |  | 0 | 11 | 41 | 8 |  |  | 14 | 8 | 13 | 13 | 1 | 7.143%
MRR P.D. Projects | 2018 Sprint 14 |  |  | 72 | 37 | 29 | 6 |  |  | 11 | 26 | 15 | 7 | 4 | 36.36%
MRR P.D. Projects | 2018 Sprint 2 |  |  | 4 |  | 2 | 2 |  |  | 19 | 15 | 0 | 3 | 16 | 84.21%
MRR P.D. Projects | 2018 Sprint 3 |  |  | 0 |  |  | 6 |  |  | 6 | 2 | 0 | 0 | 6 | 100%
MRR P.D. Projects | 2018 Sprint 4 |  |  | 3 | 2 | 1 | 5 |  |  | 15 | 17 | 3 | 2 | 13 | 86.67%
MRR P.D. Projects | 2018 Sprint 5 |  |  | 3 | 5 | 4 | 5 |  |  | 15 | 10 | 3 | 2 | 13 | 86.67%
MRR P.D. Projects | 2018 Sprint 6 |  |  | 8.5 | 8 | 3 | 5.5 |  |  | 9 | 9 | 2 | 4 | 5 | 55.56%
MRR P.D. Projects | 2018 Sprint 7 |  |  | 12 | 2 | 3 | 14 |  |  | 20 | 13 | 4 | 3 | 17 | 85%
MRR P.D. Projects | 2018 Sprint 8 |  |  | 7 | 5 |  | 2 |  |  | 4 | 7 | 4 | 0 | 4 | 100%
MRR P.D. Projects | 2018 Sprint 9 | 1 |  | 26 |  | 3 | 24 |  | 2400% | 6 | 5 | 0 | 1 | 5 | 83.33%
MRR P.D. Projects | 2018 Star Sprint 01 |  |  | 0 | 21 |  | 22 |  |  | 8 | 1 | 4 | 0 | 8 | 100%
MRR P.D. Projects | 2018 Star Sprint 2 |  |  | 18 | 3 | 13 | 8 |  |  | 9 | 8 | 1 | 3 | 6 | 66.67%
MRR P.D. Projects | 2018 Star Sprint 3 |  |  | 15 | 3 | 3 | 23 |  |  | 9 | 5 | 1 | 1 | 8 | 88.89%
MRR P.D. Projects | 2018 Star Sprint 4 |  |  | 1 |  | 6 | 6 |  |  | 5 | 1 | 0 | 3 | 2 | 40%
MRR P.D. Projects | MRR- Sprint 41 |  |  | 0 | [5 empty] | 1 | 1 | 0 | 0 | 1 | 100%
MRR P.D. Projects | MRR- Sprint 42 |  |  | 0 |  |  | 3 |  |  | 2 | 0 | 0 | 1 | 1 | 50%
MRR P.D. Projects | MRR- Sprint 43 |  |  | 0 | [5 empty] | 1 | 1 | 0 | 0 | 1 | 100%
MRR P.D. Projects | MRR- Sprint 44 |  |  | 0 | [5 empty] | 2 | 2 | 0 | 2 | 0 | 0%
MRR P.D. Projects | MRR- Sprint 45 |  |  | 0 | [5 empty] | 2 | 2 | 0 | 2 | 0 | 0%
MRR P.D. Projects | MRR- Sprint 46 |  |  | 16 | 3 | 9 | 6 |  |  | 10 | 8 | 2 | 4 | 6 | 60%
MRR P.D. Projects | MRR- Sprint 47 |  |  | 17 | 3 |  | 51.5 |  |  | 21 | 11 | 1 | 0 | 21 | 100%
MRR P.D. Projects | MRR- Sprint 48 |  |  | 10 |  | 5 | 53 |  |  | 11 | 4 | 0 | 1 | 10 | 90.91%
MRR P.D. Projects | RAPS-EDPS 2017 Sprint 15 |  |  | 0 | [5 empty] | 1 | 1 | 0 | 0 | 1 | 100%
MRR Production Support | 2017 BP Sprint 25 |  |  | 0 | [5 empty] | 1 | 1 | 0 | 0 | 1 | 100%
MRR Production Support | 2017 Sprint 12 |  |  | 0 |  |  | 5 |  |  | 34 | 20 | 5 | 0 | 34 | 100%
MRR Production Support | 2017 Sprint 13 |  |  | 0 | [5 empty] | 12 | 2 | 3 | 4 | 8 | 66.67%
MRR Production Support | 2017 Sprint 14 |  |  | 0 | [5 empty] | 6 | 7 | 6 | 1 | 5 | 83.33%
MRR Production Support | 2017 Sprint 15 |  |  | 0 | 2 |  |  |  |  | 12 | 7 | 2 | 0 | 12 | 100%
MRR Production Support | 2017 Sprint 16 |  |  | 9 | 6 |  | 9 |  |  | 18 | 13 | 5 | 1 | 17 | 94.44%
MRR Production Support | 2017 Sprint 17 |  |  | 0 | 6 |  |  |  |  | 7 | 5 | 6 | 2 | 5 | 71.43%
MRR Production Support | 2017 Sprint 18 |  |  | 3 | 3 |  | 8 |  |  | 7 | 4 | 1 | 0 | 7 | 100%
MRR Production Support | 2017 Sprint 19 |  |  | 2 | 3 | 3 | 5 |  |  | 3 | 2 | 2 | 1 | 2 | 66.67%
MRR Production Support | 2017 Sprint 20 |  |  | 1 |  |  | 4 |  |  | 12 | 10 | 4 | 1 | 11 | 91.67%
MRR Production Support | 2017 Sprint 21 |  |  | 0 | [5 empty] | 5 | 7 | 4 | 1 | 4 | 80%
MRR Production Support | 2017 Sprint 22 |  |  | 0 |  | 5 |  |  |  | 16 | 9 | 1 | 3 | 13 | 81.25%
MRR Production Support | 2017 Sprint 23 |  |  | 5 |  | 5 | 3 |  |  | 7 | 5 | 1 | 2 | 5 | 71.43%
MRR Production Support | 2017 Sprint 24 |  |  | 8 |  |  | 8 |  |  | 7 | 8 | 1 | 0 | 7 | 100%
MRR Production Support | 2017 Sprint 25 |  |  | 0 |  |  | 10 |  |  | 5 | 1 | 1 | 0 | 5 | 100%
MRR Production Support | 2017 Star Sprint 19 |  |  | 0 |  |  | 2 |  |  | 1 | 0 | 0 | 0 | 1 | 100%
MRR Production Support | 2017 Star Sprint 20 |  |  | 2 |  | 3 | 6 |  |  | 8 | 5 | 0 | 2 | 6 | 75%
MRR Production Support | 2017 Star Sprint 21 |  |  | 3 |  |  | 3 |  |  | 11 | 3 | 0 | 3 | 8 | 72.73%
MRR Production Support | 2017 Star Sprint 22 |  |  | 0 | [5 empty] | 7 | 5 | 0 | 3 | 4 | 57.14%
MRR Production Support | 2017 Star Sprint 23 |  |  | 2 | 5 |  | 16 |  |  | 9 | 6 | 2 | 3 | 6 | 66.67%
MRR Production Support | 2017 Star Sprint 24 |  |  | 5 | 10 |  | 7 |  |  | 12 | 7 | 4 | 0 | 12 | 100%
MRR Production Support | 2017 Star Sprint 25 |  |  | 1 | 1 |  | 18 |  |  | 6 | 3 | 2 | 0 | 6 | 100%
MRR Production Support | 2017 Star Sprint 26 |  |  | 0 | 2 |  |  |  |  | 2 | 2 | 1 | 0 | 2 | 100%
MRR Production Support | 2018 Sprint 1 |  |  | 0 | [5 empty] | 1 | 1 | 0 | 0 | 1 | 100%
MRR Production Support | 2018 Sprint 10 |  |  | 9 | 2 |  | 7 |  |  | 2 | 3 | 1 | 0 | 2 | 100%
MRR Production Support | 2018 Sprint 11 |  |  | 3 | 3 |  |  |  |  | 2 | 3 | 1 | 0 | 2 | 100%
MRR Production Support | 2018 Sprint 12 |  |  | 1 |  |  | 1 |  |  | 2 | 3 | 1 | 0 | 2 | 100%
MRR Production Support | 2018 Sprint 13 |  |  | 0 | [5 empty] | 0 | 1 | 1 | 0 | 0
MRR Production Support | 2018 Sprint 14 |  |  | 7 | 7 |  |  |  |  | 0 | 2 | 2 | 0 | 0
MRR Production Support | 2018 Sprint 15 |  |  | 3 | 3 |  |  |  |  | 0 | 1 | 1 | 0 | 0
MRR Production Support | 2018 Sprint 16 |  |  | 0 | [5 empty] | 1 | 2 | 0 | 0 | 1 | 100%
MRR Production Support | 2018 Sprint 17 |  |  | 0 | 3 |  |  |  |  | 12 | 16 | 4 | 1 | 11 | 91.67%
MRR Production Support | 2018 Sprint 18 |  |  | 0 | [5 empty] | 3 | 5 | 1 | 1 | 2 | 66.67%
MRR Production Support | 2018 Sprint 2 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
MRR Production Support | 2018 Sprint 3 |  |  | 0 |  |  | 8 |  |  | 6 | 4 | 0 | 0 | 6 | 100%
MRR Production Support | 2018 Sprint 4 |  |  | 0 |  | 6 |  |  |  | 4 | 0 | 0 | 2 | 2 | 50%
MRR Production Support | 2018 Sprint 5 |  |  | 10 |  | 2 | 21 |  |  | 11 | 5 | 0 | 1 | 10 | 90.91%
MRR Production Support | 2018 Sprint 6 |  |  | 1 |  |  | 3 |  |  | 5 | 4 | 0 | 1 | 4 | 80%
MRR Production Support | 2018 Sprint 7 | 4 |  | 11 |  | 3 | 12 |  | 300% | 7 | 5 | 0 | 1 | 6 | 85.71%
MRR Production Support | 2018 Sprint 8 |  |  | 3 | 3 |  |  |  |  | 0 | 2 | 4 | 0 | 0
MRR Production Support | 2018 Sprint 9 |  |  | 13 | 13 |  |  |  |  | 1 | 3 | 2 | 0 | 1 | 100%
MRR Production Support | 2018 Star Sprint 01 |  |  | 0 |  |  | 16 |  |  | 9 | 2 | 0 | 0 | 9 | 100%
MRR Production Support | 2018 Star Sprint 2 |  |  | 0 | [5 empty] | 5 | 2 | 0 | 1 | 4 | 80%
MRR Production Support | 2018 Star Sprint 3 |  |  | 0 |  |  | 6 |  |  | 10 | 3 | 0 | 1 | 9 | 90%
MRR Production Support | 2018 Star Sprint 4 |  |  | 0 |  |  | 7 |  |  | 8 | 6 | 0 | 0 | 8 | 100%
MRR Production Support | MRR- Sprint 36 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
MRR Production Support | MRR- Sprint 38 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
MRR Production Support | MRR- Sprint 46 |  |  | 1 |  |  | 1 |  |  | 4 | 3 | 10 | 0 | 4 | 100%
MRR Production Support | MRR- Sprint 47 |  |  | 0 | [5 empty] | 34 | 25 | 3 | 7 | 27 | 79.41%
MRR Production Support | MRR- Sprint 48 |  |  | 0 |  |  | 1 |  |  | 21 | 13 | 6 | 6 | 15 | 71.43%
MRR Small Enhancements | 2017 Sprint 12 |  |  | 0 |  |  | 5 |  |  | 2 | 0 | 2 | 0 | 2 | 100%
MRR Small Enhancements | 2017 Sprint 13 | 5 |  | 5 |  | 5 | 5 |  | 100% | 3 | 1 | 0 | 2 | 1 | 33.33%
MRR Small Enhancements | 2017 Sprint 14 |  |  | 5 |  |  | 5 |  |  | 1 | 1 | 0 | 0 | 1 | 100%
MRR Small Enhancements | 2017 Sprint 16 |  |  | 3 |  |  | 9 |  |  | 3 | 1 | 0 | 0 | 3 | 100%
MRR Small Enhancements | 2017 Sprint 17 |  |  | 0 |  |  | 8 |  |  | 2 | 0 | 0 | 0 | 2 | 100%
MRR Small Enhancements | 2017 Sprint 18 | 21 |  | 0 |  | 5 | 16 |  | 76.19% | 7 | 0 | 0 | 1 | 6 | 85.71%
MRR Small Enhancements | 2017 Sprint 19 |  |  | 5 |  |  | 18 |  |  | 5 | 1 | 0 | 0 | 5 | 100%
MRR Small Enhancements | 2017 Sprint 20 |  |  | 8 |  | 3 | 5 |  |  | 3 | 1 | 0 | 1 | 2 | 66.67%
MRR Small Enhancements | 2017 Sprint 21 |  |  | 0 |  |  | 2 |  |  | 1 | 0 | 0 | 0 | 1 | 100%
MRR Small Enhancements | 2017 Sprint 23 | 13 |  | 0 |  | 8 | 5 |  | 38.46% | 3 | 0 | 0 | 2 | 1 | 33.33%
MRR Small Enhancements | 2017 Sprint 24 |  |  | 13 | 5 |  | 8 |  |  | 2 | 3 | 1 | 0 | 2 | 100%
MRR Small Enhancements | 2017 Sprint 26 |  |  | 0 |  |  | 4 |  |  | 2 | 0 | 0 | 0 | 2 | 100%
MRR Small Enhancements | 2017 Star Sprint 21 |  |  | 0 |  |  | 2 |  |  | 1 | 0 | 0 | 0 | 1 | 100%
MRR Small Enhancements | 2017 Star Sprint 23 |  |  | 0 |  |  | 5 |  |  | 1 | 0 | 0 | 0 | 1 | 100%
MRR Small Enhancements | 2018 Sprint 1 |  |  | 3 | 10 |  | 19 |  |  | 6 | 1 | 2 | 0 | 6 | 100%
MRR Small Enhancements | 2018 Sprint 10 |  |  | 36 | 31 | 5 |  |  |  | 1 | 6 | 5 | 1 | 0 | 0%
MRR Small Enhancements | 2018 Sprint 11 |  |  | 10 | 5 | 5 |  |  |  | 1 | 2 | 1 | 1 | 0 | 0%
MRR Small Enhancements | 2018 Sprint 12 |  |  | 5 | 5 |  |  |  |  | 0 | 1 | 1 | 0 | 0
MRR Small Enhancements | 2018 Sprint 14 |  |  | 3 |  | 3 |  |  |  | 1 | 1 | 0 | 1 | 0 | 0%
MRR Small Enhancements | 2018 Sprint 15 |  |  | 3 | 3 |  |  |  |  | 0 | 1 | 1 | 0 | 0
MRR Small Enhancements | 2018 Sprint 17 |  |  | 0 | 3 |  |  |  |  | 0 | 0 | 1 | 0 | 0
MRR Small Enhancements | 2018 Sprint 2 | 39 |  | 0 | 3 | 5 | 34 |  | 87.18% | 9 | 0 | 1 | 1 | 8 | 88.89%
MRR Small Enhancements | 2018 Sprint 20 |  |  | 6 | 3 |  | 3 |  |  | 1 | 2 | 1 | 0 | 1 | 100%
MRR Small Enhancements | 2018 Sprint 26 |  |  | 3 | 3 |  |  |  |  | 0 | 1 | 1 | 0 | 0
MRR Small Enhancements | 2018 Sprint 3 | 26.5 |  | 3 |  | 8 | 21.5 |  | 81.13% | 7 | 1 | 0 | 1 | 6 | 85.71%
MRR Small Enhancements | 2018 Sprint 4 |  |  | 11 | 3 | 16 | 22 |  |  | 8 | 2 | 1 | 3 | 5 | 62.5%
MRR Small Enhancements | 2018 Sprint 5 | 40 |  | 19 |  | 16 | 43 |  | 107.5% | 12 | 3 | 0 | 2 | 10 | 83.33%
MRR Small Enhancements | 2018 Sprint 6 |  |  | 16 |  | 3 | 21 |  |  | 5 | 4 | 0 | 1 | 4 | 80%
MRR Small Enhancements | 2018 Sprint 7 |  |  | 5 |  | 8 | 3 |  |  | 7 | 4 | 0 | 3 | 4 | 57.14%
MRR Small Enhancements | 2018 Sprint 8 |  |  | 51 | 43 | 8 |  |  |  | 2 | 14 | 14 | 1 | 1 | 50%
MRR Small Enhancements | 2018 Sprint 9 |  |  | 27 | 14 | 13 |  |  |  | 2 | 6 | 4 | 2 | 0 | 0%
MRR Small Enhancements | 2018 Star Sprint 01 |  |  | 3 | 1 |  | 2 |  |  | 3 | 4 | 1 | 0 | 3 | 100%
MRR Small Enhancements | 2018 Star Sprint 2 | 19 |  | 1 |  | 16 | 2 |  | 10.53% | 5 | 1 | 0 | 3 | 2 | 40%
MRR Small Enhancements | 2018 Star Sprint 3 | 16 |  | 13 |  | 8 | 24 |  | 150% | 8 | 2 | 0 | 1 | 7 | 87.5%
MRR Small Enhancements | 2018 Star Sprint 4 |  |  | 8 |  | 21 | 8 |  |  | 8 | 4 | 0 | 4 | 4 | 50%
MRR Small Enhancements | 2019 Sprint 1 |  |  | 14 | 14 |  |  |  |  | 0 | 5 | 5 | 0 | 0
MRR Small Enhancements | 2019 Sprint 11 |  |  | 8 |  | 8 |  |  |  | 1 | 1 | 0 | 1 | 0 | 0%
MRR Small Enhancements | 2019 Sprint 12 |  |  | 9 | 9 |  | 8 |  |  | 1 | 2 | 3 | 0 | 1 | 100%
MRR Small Enhancements | 2019 Sprint 13 Wicked Smaht |  |  | 0 | 5 |  |  |  |  | 0 | 0 | 1 | 0 | 0
MRR Small Enhancements | 2019 Sprint 2 |  |  | 30 | 14 |  | 16 |  |  | 4 | 8 | 4 | 0 | 4 | 100%
MRR Small Enhancements | 2019 Sprint 3 |  |  | 3 | 3 |  |  |  |  | 0 | 2 | 2 | 0 | 0
MRR Small Enhancements | 2019 Sprint 5 |  |  | 0 | 5 |  |  |  |  | 0 | 0 | 1 | 0 | 0
MRR Small Enhancements | 2019 Sprint 7 |  |  | 0 | 3 |  | 1 |  |  | 1 | 0 | 1 | 0 | 1 | 100%
MRR Small Enhancements | 2019 Sprint 8 |  |  | 5 | 6 |  |  |  |  | 0 | 1 | 2 | 0 | 0
MRR Small Enhancements | 2019 Sprint 9 |  |  | 0 | 36 |  |  |  |  | 0 | 0 | 10 | 0 | 0
MRR Small Enhancements | MRR- Sprint 44 |  |  | 2 |  |  | 2 |  |  | 1 | 1 | 0 | 0 | 1 | 100%
MRR Small Enhancements | MRR- Sprint 46 |  |  | 5 | 3 | 6 | 3 |  |  | 5 | 3 | 4 | 3 | 2 | 40%
MRR Small Enhancements | MRR- Sprint 47 |  |  | 11 | 1 | 3 | 29 |  |  | 11 | 6 | 1 | 1 | 10 | 90.91%
MRR Small Enhancements | MRR- Sprint 48 |  |  | 3 |  |  | 4 |  |  | 3 | 2 | 0 | 0 | 3 | 100%
MRR Small Enhancements | Sprint 25 |  |  | 0 | [5 empty] | 3 | 1 | 2 | 0 | 3 | 100%
OR board | Team Raider Sprint 14 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
QA board | Emblem Medicaid |  | 0 | 0 |  |  |  | 0 |  | 7 | 2 | 1 | 0 | 7 | 100%
QA board | Highmark Implementation |  | 0 | 0 |  |  |  | 0 |  | 26 | 19 | 2 | 18 | 8 | 30.77%
QME P.D. Projects | 2017 QME Sprint 16 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
QME P.D. Projects | 2017 QME Sprint 17 |  |  | 58 | 58 |  |  |  |  | 0 | 17 | 17 | 0 | 0
QME P.D. Projects | 2017 QME Sprint 18 |  |  | 91 | 70 | 21 |  |  |  | 6 | 22 | 17 | 6 | 0 | 0%
QME P.D. Projects | 2017 QME Sprint 19 |  |  | 53 | 63 | 8 |  |  |  | 2 | 29 | 31 | 1 | 1 | 50%
QME P.D. Projects | 2017 QME Sprint 20 |  |  | 181 | 143 | 36 |  |  |  | 12 | 48 | 36 | 12 | 0 | 0%
QME P.D. Projects | 2017 QME Sprint 21 |  |  | 148 | 175 | 5 |  |  |  | 4 | 26 | 31 | 4 | 0 | 0%
QME P.D. Projects | 2017 QME Sprint 22 |  |  | 153 | 153 | 10 |  |  |  | 6 | 31 | 30 | 4 | 2 | 33.33%
QME P.D. Projects | 2017 QME Sprint 23 |  |  | 138 | 148 | 8 |  |  |  | 3 | 24 | 25 | 2 | 1 | 33.33%
QME P.D. Projects | 2017 QME Sprint 24 |  |  | 151 | 143 | 8 | 3 |  |  | 4 | 52 | 48 | 3 | 1 | 25%
QME P.D. Projects | 2017 QME Sprint 25 |  |  | 132 | 148 |  |  |  |  | 4 | 32 | 30 | 2 | 2 | 50%
QME P.D. Projects | 2017 QME Sprint 26 |  |  | 55 | 44 | 16 |  |  |  | 12 | 13 | 11 | 6 | 6 | 50%
QME P.D. Projects | 2018 QME Sprint 1 |  |  | 113 | 113 | 16 |  |  |  | 12 | 24 | 23 | 5 | 7 | 58.33%
QME P.D. Projects | 2018 QME Sprint 2 |  |  | 137 | 103 | 35 |  |  |  | 10 | 30 | 21 | 6 | 4 | 40%
QME P.D. Projects | 2018 QME Sprint 3 |  |  | 113 | 92 | 21 |  |  |  | 8 | 29 | 21 | 7 | 1 | 12.5%
QME P.D. Projects | 2018 QME Sprint 4 |  |  | 68 | 58 | 10 |  |  |  | 9 | 35 | 27 | 7 | 2 | 22.22%
QME P.D. Projects | 2018 QME Sprint 5 |  |  | 68 | 53 | 25 |  |  |  | 14 | 26 | 20 | 8 | 6 | 42.86%
QME P.D. Projects | 2018 QME Sprint 6 |  |  | 48 | 64 | 5 |  |  |  | 6 | 19 | 21 | 3 | 3 | 50%
QME P.D. Projects | Kerbal Sprint 16 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
QME P.D. Projects | Kerbal Sprint 17 IP |  |  | 0 | [5 empty] | 1 | 0 | 0 | 1 | 0 | 0%
QME P.D. Projects | Kerbal Sprint 18 |  |  | 0 | [5 empty] | 1 | 1 | 0 | 1 | 0 | 0%
QME P.D. Projects | Tech Enablement QME Backlog |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0