## Sprint Report
Team | Sprint | State | Story Points Committed | Story Ponts Committed VC | Story Points Added | Story Points Removed | Story Points Not Completed | Story Points Completed | Story Points Completed VC | % Complete | # Issues Committed | # Issues Added | # Issues Removed | # Issues Not Completed | # Issues Completed | % Complete
IDAP Scrum Board (AbracaData) | Sprint 5 (IDAP 2020) | CLOSED | 41 |  | 16 | 30 | 8 | 8 |  | 0.19512 | 8 | 13 | 10 | 3 | 8 | 1
IDAP Scrum Board (AbracaData) | Sprint 0 (IDAP 2020) | CLOSED | 35 |  | 8 | 21 |  | 30 |  | 0.85714 | 10 | 1 | 4 | 0 | 7 | 0.7
IDAP Scrum Board (AbracaData) | Sprint 6 (IDAP 2020) | CLOSED | 24 |  | 0 | 16 | 8 |  |  |  | 7 | 2 | 5 | 1 | 3 | 0.42857
IDAP Scrum Board (AbracaData) | Sprint 7 (IDAP 2020) | CLOSED | 42 |  | 3 | 21 |  | 16 |  | 0.38095 | 8 | 2 | 7 | 0 | 3 | 0.375
IDAP Scrum Board (AbracaData) | Sprint 8 (IDAP 2020) | CLOSED | 28 |  | 0 |  | 10 | 18 |  | 0.64286 | 9 | 1 | 2 | 3 | 5 | 0.55556
IDAP Scrum Board (AbracaData) | Sprint 9 (IDAP 2020) | CLOSED | 33 |  | 0 | 13 |  | 20 |  | 0.60606 | 11 | 2 | 5 | 0 | 8 | 0.72727
IDAP Scrum Board (AbracaData) | Sprint 10 (IDAP 2020) | CLOSED | 34 |  | 0 |  |  | 34 |  | 1 | 11 | 1 | 3 | 1 | 8 | 0.72727
IDAP Scrum Board (AbracaData) | Sprint 11 (IDAP 2020) | CLOSED | 23 |  | 0 | 5 |  | 23 |  | 1 | 9 | 1 | 4 | 0 | 6 | 0.66667
IDAP Scrum Board (AbracaData) | 2020 Sprint 12 - Team 42 | CLOSED | 32 |  | 0 | 1 | 26 | 5 |  | 0.15625 | 6 | 2 | 1 | 5 | 2 | 0.33333
IDAP Scrum Board (AbracaData) | Sprint 13 (IDAP 2020) | CLOSED | 31 |  | 10 | 13 |  | 28 |  | 0.90323 | 5 | 4 | 3 | 0 | 6 | 1.2
IDAP Scrum Board (AbracaData) | Sprint 14 (IDAP 2020) | CLOSED | 45 |  | 0 | 16 |  | 27 |  | 0.6 | 10 | 0 | 3 | 0 | 7 | 0.7
IDAP Scrum Board (AbracaData) | Sprint 15 (IDAP 2020) | CLOSED | 48 |  | 0 | 13 |  | 19 |  | 0.39583 | 9 | 0 | 4 | 0 | 5 | 0.55556
IDAP Scrum Board (AbracaData) | Sprint 16 (IDAP 2020) | CLOSED | 29 |  | 0 | 13 |  | 5 |  | 0.17241 | 5 | 0 | 4 | 0 | 1 | 0.2
IDAP Scrum Board (AbracaData) | Sprint 17 (IDAP 2020) | CLOSED | 22 |  | 11 | 8 |  | 25 |  | 1.1364 | 6 | 4 | 3 | 0 | 7 | 1.1667
IDAP Scrum Board (AbracaData) | Sprint 18 (IDAP 2020) | CLOSED | 21 |  | 20 | 11 |  | 24 |  | 1.1429 | 10 | 10 | 7 | 0 | 13 | 1.3
IDAP Scrum Board (AbracaData) | Sprint 19 (IDAP 2020) | CLOSED | 27 |  | 5 | 6 | 5 | 22 |  | 0.81481 | 9 | 3 | 3 | 1 | 8 | 0.88889
IDAP Scrum Board (AbracaData) | Sprint 20 (IDAP 2020) | CLOSED | 26 |  | 0 |  | 3 | 23 |  | 0.88462 | 10 | 1 | 0 | 2 | 9 | 0.9
IDAP Scrum Board (AbracaData) | Sprint 21 (IDAP 2020) | CLOSED | 24 |  | 1 |  |  | 25 |  | 1.0417 | 11 | 1 | 0 | 3 | 9 | 0.81818
IDAP Scrum Board (AbracaData) | Sprint 22 (IDAP 2020) | CLOSED | 23 |  | 0 |  |  | 23 |  | 1 | 9 | 0 | 0 | 2 | 7 | 0.77778
IDAP Scrum Board (AbracaData) | Sprint 23 (IDAP 2020) | CLOSED | 37 |  | 3 |  |  | 40 |  | 1.0811 | 11 | 1 | 0 | 1 | 11 | 1
IDAP Scrum Board (AbracaData) | Sprint 24 (IDAP 2020) | CLOSED | 45 |  | 0 |  |  | 37 |  | 0.82222 | 9 | 1 | 1 | 1 | 8 | 0.88889
IDAP Scrum Board (AbracaData) | Sprint 25 (IDAP 2020) | CLOSED | 39 |  | 0 |  | 8 | 31 |  | 0.79487 | 10 | 4 | 1 | 1 | 12 | 1.2
IDAP Scrum Board (AbracaData) | Sprint 26 (IDAP 2020) | CLOSED | 38 |  | 0 |  |  | 38 |  | 1 | 6 | 3 | 0 | 1 | 8 | 1.3333
IDAP Scrum Board (AbracaData) | Sprint 1 (IDAP 2021) | CLOSED | 39 |  | 0 |  |  | 39 |  | 1 | 7 | 0 | 0 | 0 | 7 | 1
IDAP Scrum Board (AbracaData) | Sprint 2 (IDAP 2021) | CLOSED | 35 |  | 0 |  |  | 35 |  | 1 | 8 | 1 | 0 | 2 | 7 | 0.875
IDAP Scrum Board (AbracaData) | Sprint 3 (IDAP 2021) | CLOSED | 43 | 46 | 8 | 7 | 5 | 44 | 44 | 1.0233 | 11 | 2 | 2 | 2 | 9 | 0.81818
IDAP Scrum Board (AbracaData) | Sprint 4 (IDAP 2021) | CLOSED | 53 | 56 | 8 |  | 8 | 53 | 53 | 1 | 14 | 1 | 0 | 4 | 11 | 0.78571
IDAP Scrum Board (AbracaData) | Sprint 5 (IDAP 2021) | CLOSED | 72 | 80 | 0 | 2 |  | 70 | 70 | 0.97222 | 19 | 1 | 1 | 3 | 16 | 0.84211
IDAP Scrum Board (AbracaData) | Sprint 6 (IDAP 2021) | CLOSED | 68 | 89 | 0 |  |  | 68 | 68 | 1 | 17 | 0 | 0 | 5 | 12 | 0.70588
IDAP Scrum Board (AbracaData) | Sprint 7 (IDAP 2021) | CLOSED | 74 | 95 | 3 |  | 13 | 64 | 64 | 0.86486 | 18 | 1 | 0 | 4 | 15 | 0.83333
IDAP Scrum Board (AbracaData) | Sprint 8 (IDAP 2021) | CLOSED | 64 | 114 | 13 | 8 | 26 | 51 | 51 | 0.79688 | 13 | 5 | 1 | 7 | 10 | 0.76923
IDAP Scrum Board (AbracaData) | Sprint 9 (IDAP 2021) | CLOSED | 100 | 150 | 4 |  | 13 | 95 | 95 | 0.95 | 25 | 2 | 0 | 9 | 18 | 0.72
IDAP Scrum Board (AbracaData) | Sprint 10 (IDAP 2021) | ACTIVE | 69 |  | 2 | 5 | 64 | 2 |  | 0.028986 | 21 | 3 | 1 | 22 | 1 | 0.047619
IDAP Scrum Board (AbracaData) | Sprint 11 (IDAP 2021) | FUTURE | 21 |  | 0 |  | 21 |  |  |  | 33 | 0 | 0 | 33 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 12 (IDAP 2021) | FUTURE | 8 |  | 0 |  | 8 |  |  |  | 2 | 0 | 0 | 2 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 13 (IDAP 2021) | FUTURE | 8 |  | 0 |  | 8 |  |  |  | 2 | 0 | 0 | 2 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 14 (IDAP 2021) | FUTURE | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 15 (IDAP 2021) | FUTURE | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 16 (IDAP 2021) | FUTURE | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 17 (IDAP 2021) | FUTURE | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 18 (IDAP 2021) | FUTURE | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 19 (IDAP 2021) | FUTURE | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 20 (IDAP 2021) | FUTURE | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 21 (IDAP 2021) | FUTURE | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 22 (IDAP 2021) | FUTURE | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 23 (IDAP 2021) | FUTURE | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 24 (IDAP 2021) | FUTURE | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 25 (IDAP 2021) | FUTURE | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 26 (IDAP 2021) | FUTURE | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0