## Sprint Report
Team | Sprint | Story Points Committed | Story Ponts Committed VC | Story Points Added | Story Points Removed | Story Points Not Completed | Story Points Completed | Story Points Completed VC | % Complete | # Issues Committed | # Issues Added | # Issues Removed | # Issues Not Completed | # Issues Completed | % Complete
IDAP Scrum Board (AbracaData) | Sprint 5 (IDAP 2020) |  |  | 16 | 30 | 8 | 8 |  |  | 11 | 13 | 10 | 3 | 8 | 0.72727
IDAP Scrum Board (AbracaData) | Sprint 0 (IDAP 2020) |  |  | 8 | 21 |  | 30 |  |  | 7 | 1 | 4 | 0 | 7 | 1
IDAP Scrum Board (AbracaData) | Sprint 6 (IDAP 2020) |  |  | 0 | 16 | 8 |  |  |  | 4 | 2 | 5 | 1 | 3 | 0.75
IDAP Scrum Board (AbracaData) | Sprint 7 (IDAP 2020) |  |  | 3 | 21 |  | 16 |  |  | 3 | 2 | 7 | 0 | 3 | 1
IDAP Scrum Board (AbracaData) | Sprint 8 (IDAP 2020) |  |  | 0 |  | 10 | 18 |  |  | 8 | 1 | 2 | 3 | 5 | 0.625
IDAP Scrum Board (AbracaData) | Sprint 9 (IDAP 2020) |  |  | 0 | 13 |  | 20 |  |  | 8 | 2 | 5 | 0 | 8 | 1
IDAP Scrum Board (AbracaData) | Sprint 10 (IDAP 2020) |  |  | 0 |  |  | 34 |  |  | 9 | 1 | 3 | 1 | 8 | 0.88889
IDAP Scrum Board (AbracaData) | Sprint 11 (IDAP 2020) |  |  | 0 | 5 |  | 23 |  |  | 6 | 1 | 4 | 0 | 6 | 1
IDAP Scrum Board (AbracaData) | 2020 Sprint 12 - Team 42 |  |  | 0 | 1 | 26 | 5 |  |  | 7 | 2 | 1 | 5 | 2 | 0.28571
IDAP Scrum Board (AbracaData) | Sprint 13 (IDAP 2020) |  |  | 10 | 13 |  | 28 |  |  | 6 | 4 | 3 | 0 | 6 | 1
IDAP Scrum Board (AbracaData) | Sprint 14 (IDAP 2020) |  |  | 0 | 16 |  | 27 |  |  | 7 | 0 | 3 | 0 | 7 | 1
IDAP Scrum Board (AbracaData) | Sprint 15 (IDAP 2020) |  |  | 0 | 13 |  | 19 |  |  | 5 | 0 | 4 | 0 | 5 | 1
IDAP Scrum Board (AbracaData) | Sprint 16 (IDAP 2020) |  |  | 0 | 13 |  | 5 |  |  | 1 | 0 | 4 | 0 | 1 | 1
IDAP Scrum Board (AbracaData) | Sprint 17 (IDAP 2020) |  |  | 11 | 8 |  | 25 |  |  | 7 | 4 | 3 | 0 | 7 | 1
IDAP Scrum Board (AbracaData) | Sprint 18 (IDAP 2020) |  |  | 20 | 11 |  | 24 |  |  | 13 | 10 | 7 | 0 | 13 | 1
IDAP Scrum Board (AbracaData) | Sprint 19 (IDAP 2020) |  |  | 5 | 6 | 5 | 22 |  |  | 9 | 3 | 3 | 1 | 8 | 0.88889
IDAP Scrum Board (AbracaData) | Sprint 20 (IDAP 2020) | 26 |  | 0 |  | 3 | 23 |  | 0.88462 | 11 | 1 | 0 | 2 | 9 | 0.81818
IDAP Scrum Board (AbracaData) | Sprint 21 (IDAP 2020) |  |  | 1 |  |  | 25 |  |  | 12 | 1 | 0 | 3 | 9 | 0.75
IDAP Scrum Board (AbracaData) | Sprint 22 (IDAP 2020) |  |  | 0 |  |  | 23 |  |  | 9 | 0 | 0 | 2 | 7 | 0.77778
IDAP Scrum Board (AbracaData) | Sprint 23 (IDAP 2020) |  |  | 3 |  |  | 40 |  |  | 12 | 1 | 0 | 1 | 11 | 0.91667
IDAP Scrum Board (AbracaData) | Sprint 24 (IDAP 2020) |  |  | 0 |  |  | 37 |  |  | 9 | 1 | 1 | 1 | 8 | 0.88889
IDAP Scrum Board (AbracaData) | Sprint 25 (IDAP 2020) |  |  | 0 |  | 8 | 31 |  |  | 13 | 4 | 1 | 1 | 12 | 0.92308
IDAP Scrum Board (AbracaData) | Sprint 26 (IDAP 2020) |  | 38 | 0 |  |  | 38 | 38 |  | 9 | 3 | 0 | 1 | 8 | 0.88889
IDAP Scrum Board (AbracaData) | Sprint 1 (IDAP 2021) |  | 39 | 0 |  |  | 39 | 39 |  | 7 | 0 | 0 | 0 | 7 | 1
IDAP Scrum Board (AbracaData) | Sprint 2 (IDAP 2021) |  | 35 | 0 |  |  | 35 | 35 |  | 9 | 1 | 0 | 2 | 7 | 0.77778
IDAP Scrum Board (AbracaData) | Sprint 3 (IDAP 2021) |  | 46 | 8 | 7 | 5 | 44 | 44 |  | 11 | 2 | 2 | 2 | 9 | 0.81818
IDAP Scrum Board (AbracaData) | Sprint 4 (IDAP 2021) |  | 56 | 8 |  | 8 | 53 | 53 |  | 15 | 1 | 0 | 4 | 11 | 0.73333
IDAP Scrum Board (AbracaData) | Sprint 5 (IDAP 2021) |  | 80 | 0 | 2 |  | 70 | 70 |  | 19 | 1 | 1 | 3 | 16 | 0.84211
IDAP Scrum Board (AbracaData) | Sprint 6 (IDAP 2021) |  | 89 | 0 |  |  | 68 | 68 |  | 17 | 0 | 0 | 5 | 12 | 0.70588
IDAP Scrum Board (AbracaData) | Sprint 7 (IDAP 2021) |  |  | 0 |  | 58 | 16 |  |  | 19 | 1 | 0 | 15 | 4 | 0.21053
IDAP Scrum Board (AbracaData) | Sprint 8 (IDAP 2021) |  |  | 0 |  | 56 |  |  |  | 17 | 0 | 0 | 17 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 9 (IDAP 2021) |  |  | 0 |  | 54 |  |  |  | 11 | 0 | 0 | 11 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 10 (IDAP 2021) |  |  | 0 |  | 13 |  |  |  | 4 | 0 | 0 | 4 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 11 (IDAP 2021) |  |  | 0 |  | 8 |  |  |  | 1 | 0 | 0 | 1 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 12 (IDAP 2021) |  |  | 0 |  | 8 |  |  |  | 1 | 0 | 0 | 1 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 13 (IDAP 2021) |  |  | 0 |  | 8 |  |  |  | 1 | 0 | 0 | 1 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 14 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 15 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 16 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 17 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 18 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 19 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 20 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 21 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 22 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 23 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 24 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 25 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 26 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0