## Sheet1
Row Labels | Sum of Story Points Committed | Sum of Story Points Completed
IDAP Scrum Board (AbracaData) | 26 | 846
Sprint 0 (IDAP 2020) |  | 30
Sprint 5 (IDAP 2020) |  | 8
Sprint 6 (IDAP 2020)
Sprint 7 (IDAP 2020) |  | 16
Sprint 8 (IDAP 2020) |  | 18
Sprint 9 (IDAP 2020) |  | 20
Sprint 10 (IDAP 2020) |  | 34
Sprint 11 (IDAP 2020) |  | 23
2020 Sprint 12 - Team 42 |  | 5
Sprint 13 (IDAP 2020) |  | 28
Sprint 14 (IDAP 2020) |  | 27
Sprint 15 (IDAP 2020) |  | 19
Sprint 16 (IDAP 2020) |  | 5
Sprint 17 (IDAP 2020) |  | 25
Sprint 18 (IDAP 2020) |  | 24
Sprint 19 (IDAP 2020) |  | 22
Sprint 20 (IDAP 2020) | 26 | 23
Sprint 21 (IDAP 2020) |  | 25
Sprint 22 (IDAP 2020) |  | 23
Sprint 23 (IDAP 2020) |  | 40
Sprint 24 (IDAP 2020) |  | 37
Sprint 25 (IDAP 2020) |  | 31
Sprint 26 (IDAP 2020) |  | 38
Sprint 1 (IDAP 2021) |  | 39
Sprint 2 (IDAP 2021) |  | 35
Sprint 4 (IDAP 2021) |  | 53
Sprint 3 (IDAP 2021) |  | 44
Sprint 5 (IDAP 2021) |  | 70
Sprint 6 (IDAP 2021) |  | 68
Sprint 7 (IDAP 2021) |  | 16
Sprint 8 (IDAP 2021)
Sprint 9 (IDAP 2021)
Sprint 10 (IDAP 2021)
Sprint 11 (IDAP 2021)
Sprint 12 (IDAP 2021)
Sprint 13 (IDAP 2021)
Sprint 14 (IDAP 2021)
Sprint 15 (IDAP 2021)
Sprint 16 (IDAP 2021)
Sprint 17 (IDAP 2021)
Sprint 18 (IDAP 2021)
Sprint 19 (IDAP 2021)
Sprint 20 (IDAP 2021)
Sprint 21 (IDAP 2021)
Sprint 22 (IDAP 2021)
Sprint 23 (IDAP 2021)
Sprint 24 (IDAP 2021)
Sprint 25 (IDAP 2021)
Sprint 26 (IDAP 2021)
Grand Total | 26 | 846

## Sprint Report
Team | Sprint | Story Points Committed | Story Ponts Committed VC | Story Points Added | Story Points Removed | Story Points Not Completed | Story Points Completed | Story Points Completed VC | % Complete | # Issues Committed | # Issues Added | # Issues Removed | # Issues Not Completed | # Issues Completed | % Complete2
IDAP Scrum Board (AbracaData) | Sprint 5 (IDAP 2020) |  |  | 16 | 30 | 8 | 8 |  |  | 11 | 13 | 10 | 3 | 8 | 0.72727
IDAP Scrum Board (AbracaData) | Sprint 0 (IDAP 2020) |  |  | 8 | 21 |  | 30 |  |  | 7 | 1 | 4 | 0 | 7 | 1
IDAP Scrum Board (AbracaData) | Sprint 6 (IDAP 2020) |  |  | 0 | 16 | 8 |  |  |  | 4 | 2 | 5 | 1 | 3 | 0.75
IDAP Scrum Board (AbracaData) | Sprint 7 (IDAP 2020) |  |  | 3 | 21 |  | 16 |  |  | 3 | 2 | 7 | 0 | 3 | 1
IDAP Scrum Board (AbracaData) | Sprint 8 (IDAP 2020) |  |  | 0 |  | 10 | 18 |  |  | 8 | 1 | 2 | 3 | 5 | 0.625
IDAP Scrum Board (AbracaData) | Sprint 9 (IDAP 2020) |  |  | 0 | 13 |  | 20 |  |  | 8 | 2 | 5 | 0 | 8 | 1
IDAP Scrum Board (AbracaData) | Sprint 10 (IDAP 2020) |  |  | 0 |  |  | 34 |  |  | 9 | 1 | 3 | 1 | 8 | 0.88889
IDAP Scrum Board (AbracaData) | Sprint 11 (IDAP 2020) |  |  | 0 | 5 |  | 23 |  |  | 6 | 1 | 4 | 0 | 6 | 1
IDAP Scrum Board (AbracaData) | 2020 Sprint 12 - Team 42 |  |  | 0 | 1 | 26 | 5 |  |  | 7 | 2 | 1 | 5 | 2 | 0.28571
IDAP Scrum Board (AbracaData) | Sprint 13 (IDAP 2020) |  |  | 10 | 13 |  | 28 |  |  | 6 | 4 | 3 | 0 | 6 | 1
IDAP Scrum Board (AbracaData) | Sprint 14 (IDAP 2020) |  |  | 0 | 16 |  | 27 |  |  | 7 | 0 | 3 | 0 | 7 | 1
IDAP Scrum Board (AbracaData) | Sprint 15 (IDAP 2020) |  |  | 0 | 13 |  | 19 |  |  | 5 | 0 | 4 | 0 | 5 | 1
IDAP Scrum Board (AbracaData) | Sprint 16 (IDAP 2020) |  |  | 0 | 13 |  | 5 |  |  | 1 | 0 | 4 | 0 | 1 | 1
IDAP Scrum Board (AbracaData) | Sprint 17 (IDAP 2020) |  |  | 11 | 8 |  | 25 |  |  | 7 | 4 | 3 | 0 | 7 | 1
IDAP Scrum Board (AbracaData) | Sprint 18 (IDAP 2020) |  |  | 20 | 11 |  | 24 |  |  | 13 | 10 | 7 | 0 | 13 | 1
IDAP Scrum Board (AbracaData) | Sprint 19 (IDAP 2020) |  |  | 5 | 6 | 5 | 22 |  |  | 9 | 3 | 3 | 1 | 8 | 0.88889
IDAP Scrum Board (AbracaData) | Sprint 20 (IDAP 2020) | 26 |  | 0 |  | 3 | 23 |  | 0.88462 | 11 | 1 | 0 | 2 | 9 | 0.81818
IDAP Scrum Board (AbracaData) | Sprint 21 (IDAP 2020) |  |  | 1 |  |  | 25 |  |  | 12 | 1 | 0 | 3 | 9 | 0.75
IDAP Scrum Board (AbracaData) | Sprint 22 (IDAP 2020) |  |  | 0 |  |  | 23 |  |  | 9 | 0 | 0 | 2 | 7 | 0.77778
IDAP Scrum Board (AbracaData) | Sprint 23 (IDAP 2020) |  |  | 3 |  |  | 40 |  |  | 12 | 1 | 0 | 1 | 11 | 0.91667
IDAP Scrum Board (AbracaData) | Sprint 24 (IDAP 2020) |  |  | 0 |  |  | 37 |  |  | 9 | 1 | 1 | 1 | 8 | 0.88889
IDAP Scrum Board (AbracaData) | Sprint 25 (IDAP 2020) |  |  | 0 |  | 8 | 31 |  |  | 13 | 4 | 1 | 1 | 12 | 0.92308
IDAP Scrum Board (AbracaData) | Sprint 26 (IDAP 2020) |  | 38 | 0 |  |  | 38 | 38 |  | 9 | 3 | 0 | 1 | 8 | 0.88889
IDAP Scrum Board (AbracaData) | Sprint 1 (IDAP 2021) |  | 39 | 0 |  |  | 39 | 39 |  | 7 | 0 | 0 | 0 | 7 | 1
IDAP Scrum Board (AbracaData) | Sprint 2 (IDAP 2021) |  | 35 | 0 |  |  | 35 | 35 |  | 9 | 1 | 0 | 2 | 7 | 0.77778
IDAP Scrum Board (AbracaData) | Sprint 3 (IDAP 2021) |  | 46 | 8 | 7 | 5 | 44 | 44 |  | 11 | 2 | 2 | 2 | 9 | 0.81818
IDAP Scrum Board (AbracaData) | Sprint 4 (IDAP 2021) |  | 56 | 8 |  | 8 | 53 | 53 |  | 15 | 1 | 0 | 4 | 11 | 0.73333
IDAP Scrum Board (AbracaData) | Sprint 5 (IDAP 2021) |  | 80 | 0 | 2 |  | 70 | 70 |  | 19 | 1 | 1 | 3 | 16 | 0.84211
IDAP Scrum Board (AbracaData) | Sprint 6 (IDAP 2021) |  | 89 | 0 |  |  | 68 | 68 |  | 17 | 0 | 0 | 5 | 12 | 0.70588
IDAP Scrum Board (AbracaData) | Sprint 7 (IDAP 2021) |  |  | 0 |  | 58 | 16 |  |  | 19 | 1 | 0 | 15 | 4 | 0.21053
IDAP Scrum Board (AbracaData) | Sprint 8 (IDAP 2021) |  |  | 0 |  | 56 |  |  |  | 17 | 0 | 0 | 17 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 9 (IDAP 2021) |  |  | 0 |  | 54 |  |  |  | 11 | 0 | 0 | 11 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 10 (IDAP 2021) |  |  | 0 |  | 13 |  |  |  | 4 | 0 | 0 | 4 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 11 (IDAP 2021) |  |  | 0 |  | 8 |  |  |  | 1 | 0 | 0 | 1 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 12 (IDAP 2021) |  |  | 0 |  | 8 |  |  |  | 1 | 0 | 0 | 1 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 13 (IDAP 2021) |  |  | 0 |  | 8 |  |  |  | 1 | 0 | 0 | 1 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 14 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 15 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 16 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 17 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 18 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 19 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 20 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 21 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 22 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 23 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 24 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 25 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
IDAP Scrum Board (AbracaData) | Sprint 26 (IDAP 2021) |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0