## Sprint Report
Team | Sprint | State | Story Points Committed | Story Ponts Committed VC | Story Points Added | Story Points Removed | Story Points Not Completed | Story Points Completed | Story Points Completed VC | % Complete | # Issues Committed | # Issues Added | # Issues Removed | # Issues Not Completed | # Issues Completed | % Complete
JAMP Team 2 | Sprint 1.4 | CLOSED | 2 | 2 | 13 |  | 8 | 2 | 2 | 1 | 1 | 1 | 0 | 1 | 1 | 1
JAMP Team 2 | Sprint 1.5 | CLOSED | 26 | 26 | 0 |  | 19 | 10 | 10 | 0.38462 | 5 | 0 | 0 | 3 | 2 | 0.4
JAMP Team 2 | Sprint 2.1 | CLOSED | 19 | 19 | 0 |  | 8 | 11 | 11 | 0.57895 | 3 | 0 | 0 | 1 | 2 | 0.66667
JAMP Team 2 | Sprint 2.2 | FUTURE | 13 |  | 0 |  | 13 |  |  |  | 1 | 0 | 0 | 1 | 0 | 0
JAMP Team 1 | Sprint 1.1 | CLOSED | 0 | 0 | 5 |  |  | 5 | 5 |  | 0 | 1 | 0 | 0 | 1
JAMP Program | Sprint 1.1 | CLOSED | 11 | 11 | 5 |  | 8 | 8 | 8 | 0.72727 | 2 | 1 | 0 | 1 | 2 | 1
JAMP Program | Sprint 1.2 | CLOSED | 8 | 8 | 8 |  | 2 | 16 | 16 | 2 | 2 | 1 | 0 | 1 | 2 | 1
JAMP Program | Sprint 1.3 | CLOSED | 5 | 5 | 3 | 3 | 3 | 2 | 2 | 0.4 | 2 | 1 | 1 | 1 | 1 | 0.5
JAMP Program | Sprint 1.4 | CLOSED | 8 | 8 | 13 |  | 13 | 5 | 5 | 0.625 | 3 | 1 | 0 | 2 | 2 | 0.66667
JAMP Program | Sprint 1.5 | CLOSED | 31 | 31 | 0 |  | 19 | 15 | 15 | 0.48387 | 6 | 0 | 0 | 3 | 3 | 0.5
JAMP Program | Sprint 2.1 | CLOSED | 19 | 19 | 0 |  | 8 | 11 | 11 | 0.57895 | 3 | 0 | 0 | 1 | 2 | 0.66667
JAMP Program | Sprint 2.2 | FUTURE | 28 |  | 0 |  | 28 |  |  |  | 4 | 0 | 0 | 4 | 0 | 0
JAMP Program | Sprint 2.3 | FUTURE | 12 |  | 0 |  | 12 |  |  |  | 3 | 0 | 0 | 3 | 0 | 0
JAMP Program | Sprint 2.4 | FUTURE | 21 |  | 0 |  | 21 |  |  |  | 6 | 0 | 0 | 6 | 0 | 0
JAMP Program | Sprint 2.5 | FUTURE | 12 |  | 0 |  | 12 |  |  |  | 4 | 0 | 0 | 4 | 0 | 0
JAMP Really Super Long Board Name That Breaks the Scripts by Causing Python Exception | Sprint 1.1 | CLOSED | 11 | 11 | 5 |  | 8 | 8 | 8 | 0.72727 | 2 | 1 | 0 | 1 | 2 | 1
JAMP Really Super Long Board Name That Breaks the Scripts by Causing Python Exception | Sprint 1.2 | CLOSED | 8 | 8 | 8 |  | 2 | 16 | 16 | 2 | 2 | 1 | 0 | 1 | 2 | 1
JAMP Really Super Long Board Name That Breaks the Scripts by Causing Python Exception | Sprint 1.3 | CLOSED | 5 | 5 | 3 | 3 | 3 | 2 | 2 | 0.4 | 2 | 1 | 1 | 1 | 1 | 0.5
JAMP Really Super Long Board Name That Breaks the Scripts by Causing Python Exception | Sprint 1.4 | CLOSED | 8 | 8 | 13 |  | 13 | 5 | 5 | 0.625 | 3 | 1 | 0 | 2 | 2 | 0.66667
JAMP Really Super Long Board Name That Breaks the Scripts by Causing Python Exception | Sprint 1.5 | CLOSED | 31 | 31 | 0 |  | 19 | 15 | 15 | 0.48387 | 6 | 0 | 0 | 3 | 3 | 0.5
JAMP Really Super Long Board Name That Breaks the Scripts by Causing Python Exception | Sprint 2.1 | CLOSED | 19 | 19 | 0 |  | 8 | 11 | 11 | 0.57895 | 3 | 0 | 0 | 1 | 2 | 0.66667
JAMP Really Super Long Board Name That Breaks the Scripts by Causing Python Exception | Sprint 2.2 | FUTURE | 28 |  | 0 |  | 28 |  |  |  | 4 | 0 | 0 | 4 | 0 | 0
JAMP Really Super Long Board Name That Breaks the Scripts by Causing Python Exception | Sprint 2.3 | FUTURE | 12 |  | 0 |  | 12 |  |  |  | 3 | 0 | 0 | 3 | 0 | 0
JAMP Really Super Long Board Name That Breaks the Scripts by Causing Python Exception | Sprint 2.4 | FUTURE | 21 |  | 0 |  | 21 |  |  |  | 6 | 0 | 0 | 6 | 0 | 0
JAMP Really Super Long Board Name That Breaks the Scripts by Causing Python Exception | Sprint 2.5 | FUTURE | 12 |  | 0 |  | 12 |  |  |  | 4 | 0 | 0 | 4 | 0 | 0