## Sprint Report
Team | Sprint | Story Points Committed | Story Ponts Committed VC | Story Points Added | Story Points Removed | Story Points Not Completed | Story Points Completed | Story Points Completed VC | % Complete | # Issues Committed | # Issues Added | # Issues Removed | # Issues Not Completed | # Issues Completed | % Complete
JAMP board | Sprint 1.1 | 11 | 11 | 5 |  | 8 | 8 | 8 | 0.72727 | 3 | 1 | 0 | 1 | 2 | 0.66667
JAMP board | Sprint 1.2 |  | 8 | 8 |  | 2 | 16 | 16 |  | 3 | 1 | 0 | 1 | 2 | 0.66667
JAMP board | Sprint 1.3 |  |  | 4 | 8 | 6 |  |  |  | 3 | 2 | 2 | 3 | 0 | 0
JAMP board | API-JAMP Sprint 1.1 |  |  | 0 |  | 90 |  |  |  | 21 | 0 | 0 | 21 | 0 | 0
JAMP board | API-JAMP Sprint 1.2 |  |  | 0 |  | 99 |  |  |  | 24 | 0 | 0 | 24 | 0 | 0
JAMP board | API-JAMP Sprint 1.3 |  |  | 0 |  | 63 |  |  |  | 21 | 0 | 0 | 21 | 0 | 0
JAMP board | API-JAMP Sprint 1.4 |  |  | 0 |  | 90 |  |  |  | 20 | 0 | 0 | 20 | 0 | 0
JAMP board | API-JAMP Sprint 1.5 |  |  | 0 |  | 66 |  |  |  | 16 | 0 | 0 | 16 | 0 | 0
JAMP board | API-JAMP Sprint 2.1 |  |  | 0 |  | 58 |  |  |  | 21 | 0 | 0 | 21 | 0 | 0
JAMP board | API-JAMP Sprint 2.2 |  |  | 0 |  | 83 |  |  |  | 24 | 0 | 0 | 24 | 0 | 0
JAMP board | API-JAMP Sprint 2.3 |  |  | 0 |  | 98 |  |  |  | 22 | 0 | 0 | 22 | 0 | 0
JAMP board | API-JAMP Sprint 2.4 |  |  | 0 |  | 99 |  |  |  | 24 | 0 | 0 | 24 | 0 | 0
JAMP board | API-JAMP Sprint 2.5 |  |  | 0 |  | 92 |  |  |  | 24 | 0 | 0 | 24 | 0 | 0
JAMP board | API-JAMP Sprint 3.1 |  |  | 0 |  | 82 |  |  |  | 21 | 0 | 0 | 21 | 0 | 0
JAMP board | API-JAMP Sprint 3.2 |  |  | 0 |  | 116 |  |  |  | 25 | 0 | 0 | 25 | 0 | 0
JAMP board | API-JAMP Sprint 3.3 |  |  | 0 |  | 86 |  |  |  | 22 | 0 | 0 | 22 | 0 | 0
JAMP board | API-JAMP Sprint 3.4 |  |  | 0 |  | 83 |  |  |  | 23 | 0 | 0 | 23 | 0 | 0
JAMP board | API-JAMP Sprint 3.5 |  |  | 0 |  | 88 |  |  |  | 21 | 0 | 0 | 21 | 0 | 0